## ToC to DS4
ToC | Description | Type | Move to DS4 | Comments
S4HK900398 | BFH - Workbench Objects - S4H to DS4 | Workbench | Yes | Included all objects from packages /BFH/HUB_CORE, /BFH/DATA_FOUNDATION, /BFH/FRAMEWORK, and /BFH/TEST_DATA. See Transport Contents for objects.
S4HK900402 | BFH - Customizing Request - S4H to DS4 | Customizing | No | All entries for customizing tables. See tab Customizing Tables for complete list of transported tables.
S4HK900416 | BFH - Dependency Objects - S4H to DS4 | Workbench | No | Zurichs's objects identified as dependencies of BFH
S4HK900417 | BFH - Interface Specific Objects - S4H to DS4 | Workbench | No | Interface Specific Objects
S4HK900418 | BFH - Lookup Tables - S4H to DS4 | Customizing | Yes | Lookup Drivers and Lookup Tables. See Transport Content for objects.

## Cutover Activities
Step | Stream | Who | When | Activity | Description
1 | Preparation | Jose |  | Move DDIC objects to allow configuration of FI Code Block
2 | Preparation | Kris |  | Configure Custom Fields in FI Code Block
3 | Transport | BOA |  | Import Transports to DS4 | Decide which transports should be moved.
4 | Transport | BOA |  | Check transport logs for any missing objects | Create new transports and document dependencies as required.
5 | Post-Transport | BOA |  | Configure /BFH/ Namespace in DS4 | Configure namespace and change Source System of /BFH/ objects to allow them to be modified.

## Configuration Tables
Table Name | Which Client to Maintain it
Customizing Tables
/BFH/CONNECTION | 180
/BFH/CONNECTOR | 180
/BFH/DATA_FIELD | 180
/BFH/DATA_SEGMNT | 180
/BFH/ERROR_TYPES | 180
/BFH/EXPRESSIONS | 180
/BFH/I_FSTAG | 180
/BFH/I_PERMAN | 180
/BFH/I_VAL_MD | 180
/BFH/LOAD_TABLES | 180
/BFH/PARAM_VAL | 180
/BFH/POLICY | 180
/BFH/POST_MATRIX | 180
/BFH/PROC_STEP | 180
/BFH/PROCESS | 180
/BFH/STEP | 180
/BFH/STRUCTURE | 180
/BFH/ERR_MASTER | 180
/BFH/IF_PROCESS | 180
/BFH/INBOUND | 180
/BFH/INT_PARAM | 180
/BFH/INT_POST | 180
/BFH/INTERFACE | 180
/BFH/LKP_DRIVERS | 180
/BFH/MAPPING | 180
/BFH/OUTBOUND | 180
/BFH/MSG_GROUP_D | 180
/BFH/MSG_GROUP | 180
/BFH/HUB_REASON | 180
/BFH/MSG_MASTER | 180
/BFH/I_AGG_RULES | 180
/BFH/VALIDATION | 180
/BFH/MASTDTA_VAL | 180
/BFH/CALC_RULE | 180
/BFH/I_CAL_RUL | 180
/BFH/I_CLONCTRL | 180
/BFH/I_F_VAL_DER | 180
/BFH/I_FLTR_EXPR | 180
/BFH/FLTR_G_ASOC | 180
/BFH/FLTR_GRP | 180
/BFH/FLTR_R_DET | 180
/BFH/FLTR_R_SET | 180
/BFH/FLTR_RULE | 180
/BFH/HUB_REASON | 180
Customizing Tables with no Automatic Transport Recording (Changeable in Production Environment)
/BFH/EM_HEADER | 181
/BFH/EM_ITEM | 181
/BFH/EM_TABFIELD | 181
/BFH/CONN_PARAMS | 181
/BFH/ENVI_PARAMS | 181
/BFH/LKP_VALUES | 181
/BFH/ITF_MSG_DEF | 181

## Transport Contents
Transport | Position | Program ID | Object Type | Object
S4HK900398 | 1 | R3TR | PROG | /BFH/COPY_CODE_PAGE
S4HK900398 | 2 | R3TR | TABL | /BFH/LOG_STEP
S4HK900398 | 3 | R3TR | DDLS | /BFH/TEST_CDS
S4HK900398 | 4 | R3TR | TABL | /BFH/RUN_LOG_S
S4HK900398 | 5 | R3TR | DTEL | /BFH/EXTRACT
S4HK900398 | 6 | R3TR | DTEL | /BFH/TRANSFORM
S4HK900398 | 7 | R3TR | DTEL | /BFH/PROCESS_EXTRACT
S4HK900398 | 8 | R3TR | DTEL | /BFH/PROCESS_TRANSFORM
S4HK900398 | 9 | R3TR | DTEL | /BFH/PROCESS_LOAD
S4HK900398 | 10 | R3TR | DTEL | /BFH/PROCESS_IDOC
S4HK900398 | 11 | R3TR | DOMA | /BFH/CONNECTION_TYPE
S4HK900398 | 12 | R3TR | DOMA | /BFH/CONNECTOR_TYPE
S4HK900398 | 13 | R3TR | DTEL | /BFH/CONNECTION_TYPE
S4HK900398 | 14 | R3TR | TABL | /BFH/RUN_LOG_IF
S4HK900398 | 15 | R3TR | TABL | /BFH/PROCESSSTEP
S4HK900398 | 16 | R3TR | DDLS | /BFH/TCFSG
S4HK900398 | 17 | R3TR | DEVC | /BFH/DATA_FOUNDATION
S4HK900398 | 18 | R3TR | DOMA | /BFH/1ALO
S4HK900398 | 19 | R3TR | DOMA | /BFH/1CPTY
S4HK900398 | 20 | R3TR | DOMA | /BFH/1DCH
S4HK900398 | 21 | R3TR | DOMA | /BFH/2DOM
S4HK900398 | 22 | R3TR | DOMA | /BFH/2LO1
S4HK900398 | 23 | R3TR | DOMA | /BFH/2LO2
S4HK900398 | 24 | R3TR | DOMA | /BFH/2NOB
S4HK900398 | 25 | R3TR | DOMA | /BFH/2UY
S4HK900398 | 26 | R3TR | DOMA | /BFH/ACCIDENT_YEAR
S4HK900398 | 27 | R3TR | DOMA | /BFH/ACTIVITY_TYPE
S4HK900398 | 28 | R3TR | DOMA | /BFH/AGNOSTIC_KEY
S4HK900398 | 29 | R3TR | DOMA | /BFH/AMOUNT
S4HK900398 | 30 | R3TR | DOMA | /BFH/AMOUNT_SIGN
S4HK900398 | 31 | R3TR | DOMA | /BFH/AMY_D
S4HK900398 | 32 | R3TR | DOMA | /BFH/AUDIT_DATE
S4HK900398 | 33 | R3TR | DOMA | /BFH/AUDIT_FLAG
S4HK900398 | 34 | R3TR | DOMA | /BFH/AUDIT_USER
S4HK900398 | 35 | R3TR | DOMA | /BFH/BALFV
S4HK900398 | 36 | R3TR | DOMA | /BFH/BOOKING_PERIOD
S4HK900398 | 37 | R3TR | PROG | /BFH/CREATE_SRC_TABL
S4HK900398 | 38 | R3TR | DOMA | /BFH/BUSINESS_RANGE
S4HK900398 | 39 | R3TR | DOMA | /BFH/BUSINESS_UNIT
S4HK900398 | 40 | R3TR | DOMA | /BFH/CALC_RULE_TYP
S4HK900398 | 41 | R3TR | DOMA | /BFH/CALENDAR_ID
S4HK900398 | 42 | R3TR | DOMA | /BFH/CAL_FVT
S4HK900398 | 43 | R3TR | DOMA | /BFH/CHAR20
S4HK900398 | 44 | R3TR | DOMA | /BFH/CHAR32
S4HK900398 | 45 | R3TR | DOMA | /BFH/CHAR50
S4HK900398 | 46 | R3TR | DOMA | /BFH/CHAR76
S4HK900398 | 47 | R3TR | DOMA | /BFH/CHECKSUM
S4HK900398 | 48 | R3TR | DOMA | /BFH/CLASS_NAME
S4HK900398 | 49 | R3TR | DOMA | /BFH/CODE_PAGE
S4HK900398 | 50 | R3TR | DOMA | /BFH/COLUMN_START_END_POSITION
S4HK900398 | 51 | R3TR | DOMA | /BFH/COLUMN_TO_FILTER
S4HK900398 | 52 | R3TR | DOMA | /BFH/COMMENTS
S4HK900398 | 53 | R3TR | DOMA | /BFH/CONNECTOR_CLASS
S4HK900398 | 54 | R3TR | DOMA | /BFH/CONNECTOR_ID
S4HK900398 | 55 | R3TR | DOMA | /BFH/COST_CENTER
S4HK900398 | 56 | R3TR | DOMA | /BFH/COVERAGE_VALID_FROM_DT
S4HK900398 | 57 | R3TR | DOMA | /BFH/COVERAGE_VALID_TO_DT
S4HK900398 | 58 | R3TR | DOMA | /BFH/COVER_END_DTE
S4HK900398 | 59 | R3TR | DOMA | /BFH/COVER_START_DTE
S4HK900398 | 60 | R3TR | DOMA | /BFH/CO_INSURANCE_COMPANY
S4HK900398 | 61 | R3TR | DOMA | /BFH/CREATED_BY
S4HK900398 | 62 | R3TR | DOMA | /BFH/CREATED_ON
S4HK900398 | 63 | R3TR | DOMA | /BFH/CURRENCY_CODE
S4HK900398 | 64 | R3TR | DOMA | /BFH/DATA_ELEMENT_NAME
S4HK900398 | 65 | R3TR | DOMA | /BFH/DATA_LENGTH
S4HK900398 | 66 | R3TR | DOMA | /BFH/DATA_TYPE
S4HK900398 | 67 | R3TR | DOMA | /BFH/DATE_FORMAT
S4HK900398 | 68 | R3TR | DOMA | /BFH/DEC10_5
S4HK900398 | 69 | R3TR | DOMA | /BFH/DEC13_2
S4HK900398 | 70 | R3TR | DOMA | /BFH/DEC18_2
S4HK900398 | 71 | R3TR | DOMA | /BFH/DEC18_3
S4HK900398 | 72 | R3TR | DOMA | /BFH/DEC18_4
S4HK900398 | 73 | R3TR | DOMA | /BFH/DEC18_6
S4HK900398 | 74 | R3TR | DOMA | /BFH/DEC19_9
S4HK900398 | 75 | R3TR | DOMA | /BFH/DEC3_3
S4HK900398 | 76 | R3TR | DOMA | /BFH/DEC4_2
S4HK900398 | 77 | R3TR | DOMA | /BFH/DEC4_4
S4HK900398 | 78 | R3TR | DOMA | /BFH/DEC6_3
S4HK900398 | 79 | R3TR | DOMA | /BFH/DEC6_4
S4HK900398 | 80 | R3TR | DOMA | /BFH/DECIMAL_FORMAT
S4HK900398 | 81 | R3TR | DOMA | /BFH/DEL_FLAG
S4HK900398 | 82 | R3TR | DOMA | /BFH/DESCRIPTION
S4HK900398 | 83 | R3TR | DOMA | /BFH/DONT_SIMULATE_POSTING
S4HK900398 | 84 | R3TR | DOMA | /BFH/DRITTE
S4HK900398 | 85 | R3TR | DOMA | /BFH/DRIVER
S4HK900398 | 86 | R3TR | DOMA | /BFH/DRIVER_VALUE15
S4HK900398 | 87 | R3TR | DOMA | /BFH/DWH_BT_RULE_DESC
S4HK900398 | 88 | R3TR | DOMA | /BFH/DWH_FILE_TYPE
S4HK900398 | 89 | R3TR | DOMA | /BFH/EM
S4HK900398 | 90 | R3TR | DOMA | /BFH/EM_ID
S4HK900398 | 91 | R3TR | DOMA | /BFH/ERROR_ACTION
S4HK900398 | 92 | R3TR | DOMA | /BFH/ERROR_DEF_1
S4HK900398 | 93 | R3TR | DOMA | /BFH/ERROR_DEF_2
S4HK900398 | 94 | R3TR | DOMA | /BFH/ERROR_LOG_ID
S4HK900398 | 95 | R3TR | DOMA | /BFH/ERROR_MESSAGE
S4HK900398 | 96 | R3TR | DOMA | /BFH/ERROR_TYP_DESCR
S4HK900398 | 97 | R3TR | DOMA | /BFH/ERR_ID
S4HK900398 | 98 | R3TR | DOMA | /BFH/ERR_TYP
S4HK900398 | 99 | R3TR | DOMA | /BFH/ERR_TYP_ID
S4HK900398 | 100 | R3TR | DOMA | /BFH/EXPRESSION
S4HK900398 | 101 | R3TR | DOMA | /BFH/FEG_ID
S4HK900398 | 102 | R3TR | DOMA | /BFH/FIELD_NAME
S4HK900398 | 103 | R3TR | DOMA | /BFH/FIELD_POSITION
S4HK900398 | 104 | R3TR | DOMA | /BFH/FIELD_STATUS
S4HK900398 | 105 | R3TR | DOMA | /BFH/FILE_NAME
S4HK900398 | 106 | R3TR | DOMA | /BFH/FILE_PREFIX
S4HK900398 | 107 | R3TR | DOMA | /BFH/FILTER_CONDITION
S4HK900398 | 108 | R3TR | DOMA | /BFH/FILTER_EXPR_ID
S4HK900398 | 109 | R3TR | DOMA | /BFH/FILTER_ID
S4HK900398 | 110 | R3TR | DOMA | /BFH/FIN_TRANSACTION_TYPE
S4HK900398 | 111 | R3TR | DOMA | /BFH/FLTR_EXPRESSION
S4HK900398 | 112 | R3TR | DOMA | /BFH/FLTR_EXPR_ID
S4HK900398 | 113 | R3TR | DOMA | /BFH/FORMAT
S4HK900398 | 114 | R3TR | DOMA | /BFH/FOUNDATION_CODE
S4HK900398 | 115 | R3TR | DOMA | /BFH/FVT
S4HK900398 | 116 | R3TR | DOMA | /BFH/FVT_ID
S4HK900398 | 117 | R3TR | DOMA | /BFH/GROUP_NAME
S4HK900398 | 118 | R3TR | DOMA | /BFH/INFA_COLUMN_NAME
S4HK900398 | 119 | R3TR | DOMA | /BFH/INSURANCE_BENCH
S4HK900398 | 120 | R3TR | DOMA | /BFH/INT2
S4HK900398 | 121 | R3TR | DOMA | /BFH/INT4
S4HK900398 | 122 | R3TR | DOMA | /BFH/INT8
S4HK900398 | 123 | R3TR | DOMA | /BFH/INTERCOMPANY_CODE
S4HK900398 | 124 | R3TR | DOMA | /BFH/INTERFACE_NO
S4HK900398 | 125 | R3TR | DOMA | /BFH/INTERFACE_NUMBER
S4HK900398 | 126 | R3TR | DOMA | /BFH/INTERFACE_STATUS
S4HK900398 | 127 | R3TR | DOMA | /BFH/IN_ID
S4HK900398 | 128 | R3TR | DOMA | /BFH/IN_OUT_ID
S4HK900398 | 129 | R3TR | DOMA | /BFH/LAYER_ID
S4HK900398 | 130 | R3TR | DOMA | /BFH/LCHAR
S4HK900398 | 131 | R3TR | DOMA | /BFH/LCHAR_1024
S4HK900398 | 132 | R3TR | DOMA | /BFH/LEGAL_ENTITY
S4HK900398 | 133 | R3TR | DOMA | /BFH/LEGAL_NON_LEGAL_Q
S4HK900398 | 134 | R3TR | DOMA | /BFH/LENGTH
S4HK900398 | 135 | R3TR | DOMA | /BFH/LEVEL
S4HK900398 | 136 | R3TR | DOMA | /BFH/LINE_ID
S4HK900398 | 137 | R3TR | DOMA | /BFH/LOB_D
S4HK900398 | 138 | R3TR | DOMA | /BFH/LOGDOCNO
S4HK900398 | 139 | R3TR | DOMA | /BFH/MAN_PROC_FLG
S4HK900398 | 140 | R3TR | DOMA | /BFH/MOVFV
S4HK900398 | 141 | R3TR | DOMA | /BFH/MSG_GROUP_ID
S4HK900398 | 142 | R3TR | DOMA | /BFH/NO_OF_DOCS_PER_PROCESS
S4HK900398 | 143 | R3TR | DOMA | /BFH/NUMC6
S4HK900398 | 144 | R3TR | DOMA | /BFH/NUM_VALUE
S4HK900398 | 145 | R3TR | DOMA | /BFH/PACKAGE_ID
S4HK900398 | 146 | R3TR | DOMA | /BFH/PACKAGE_ID_NR
S4HK900398 | 147 | R3TR | DOMA | /BFH/PACKED_FORMAT
S4HK900398 | 148 | R3TR | DOMA | /BFH/PARALLEL
S4HK900398 | 149 | R3TR | DOMA | /BFH/PARAMETER_NAME
S4HK900398 | 150 | R3TR | DOMA | /BFH/PARAMETER_VALUE
S4HK900398 | 151 | R3TR | DOMA | /BFH/PARAM_NAME
S4HK900398 | 152 | R3TR | DOMA | /BFH/PARAM_VALUE
S4HK900398 | 153 | R3TR | DOMA | /BFH/PENSION_INDICATOR
S4HK900398 | 154 | R3TR | DOMA | /BFH/PERSISTENCE_POLICY
S4HK900398 | 155 | R3TR | DOMA | /BFH/PROCESS_CLASS
S4HK900398 | 156 | R3TR | DOMA | /BFH/PROCESS_RUN_ID
S4HK900398 | 157 | R3TR | DOMA | /BFH/PROCESS_STEP_ID
S4HK900398 | 158 | R3TR | DOMA | /BFH/REASON_CODE
S4HK900398 | 159 | R3TR | DOMA | /BFH/RECORD_COUNT
S4HK900398 | 160 | R3TR | DOMA | /BFH/RESULT_HIER_LEVEL_1
S4HK900398 | 161 | R3TR | DOMA | /BFH/RESULT_HIER_LEVEL_2
S4HK900398 | 162 | R3TR | DOMA | /BFH/RESULT_HIER_LEVEL_3
S4HK900398 | 163 | R3TR | DOMA | /BFH/REVERSAL_STATUS
S4HK900398 | 164 | R3TR | DOMA | /BFH/RE_INSURANCE_CODE
S4HK900398 | 165 | R3TR | DOMA | /BFH/ROLE
S4HK900398 | 166 | R3TR | DOMA | /BFH/ROW_DELIMITER
S4HK900398 | 167 | R3TR | DOMA | /BFH/RULES_VERSION_NO
S4HK900398 | 168 | R3TR | DOMA | /BFH/RULE_ID
S4HK900398 | 169 | R3TR | DOMA | /BFH/RUN_ID
S4HK900398 | 170 | R3TR | DOMA | /BFH/RUN_TYPE
S4HK900398 | 171 | R3TR | DOMA | /BFH/S1_SIM_UNTIL_FIRST_ERROR
S4HK900398 | 172 | R3TR | DOMA | /BFH/SAP_END_DTE
S4HK900398 | 173 | R3TR | DOMA | /BFH/SCHED_LAST_DATE
S4HK900398 | 174 | R3TR | DOMA | /BFH/SEGMENT_NAME
S4HK900398 | 175 | R3TR | DOMA | /BFH/SEQUENCE
S4HK900398 | 176 | R3TR | DOMA | /BFH/SIGN
S4HK900398 | 177 | R3TR | DOMA | /BFH/SOURCE
S4HK900398 | 178 | R3TR | DOMA | /BFH/SOURCE_RULE_NO
S4HK900398 | 179 | R3TR | DOMA | /BFH/SOURCE_SYSTEM
S4HK900398 | 180 | R3TR | DOMA | /BFH/STAGE
S4HK900398 | 181 | R3TR | DOMA | /BFH/START_POS
S4HK900398 | 182 | R3TR | DOMA | /BFH/STATUS_FLAG
S4HK900398 | 183 | R3TR | DOMA | /BFH/STEP_ID
S4HK900398 | 184 | R3TR | DOMA | /BFH/TABLE_NAME
S4HK900398 | 185 | R3TR | DOMA | /BFH/TARGET
S4HK900398 | 186 | R3TR | DOMA | /BFH/TECHNICAL_MESSAGE
S4HK900398 | 187 | R3TR | DOMA | /BFH/TEST_MODE
S4HK900398 | 188 | R3TR | DOMA | /BFH/TEXT15
S4HK900398 | 189 | R3TR | DOMA | /BFH/TRAD_PRTNR_STAT
S4HK900398 | 190 | R3TR | DOMA | /BFH/TYPE_OF_BUSINESS
S4HK900398 | 191 | R3TR | DOMA | /BFH/TYPE_OF_POSTING
S4HK900398 | 192 | R3TR | DOMA | /BFH/UNION_VIEW_NAME
S4HK900398 | 193 | R3TR | DOMA | /BFH/VALUE
S4HK900398 | 194 | R3TR | DOMA | /BFH/VALUE_FROM
S4HK900398 | 195 | R3TR | DOMA | /BFH/VALUE_TO
S4HK900398 | 196 | R3TR | DOMA | /BFH/XUDATFM
S4HK900398 | 197 | R3TR | DTEL | /BFH/1ALO
S4HK900398 | 198 | R3TR | DTEL | /BFH/1CPTY
S4HK900398 | 199 | R3TR | DTEL | /BFH/1DCH
S4HK900398 | 200 | R3TR | DTEL | /BFH/2DOM
S4HK900398 | 201 | R3TR | DTEL | /BFH/2LO1
S4HK900398 | 202 | R3TR | DTEL | /BFH/2LO2
S4HK900398 | 203 | R3TR | DTEL | /BFH/2NOB
S4HK900398 | 204 | R3TR | DTEL | /BFH/2UY
S4HK900398 | 205 | R3TR | DTEL | /BFH/ACCIDENT_YEAR
S4HK900398 | 206 | R3TR | DTEL | /BFH/ACC_DRIVER_VAL1
S4HK900398 | 207 | R3TR | DTEL | /BFH/ACC_DRIVER_VAL2
S4HK900398 | 208 | R3TR | DTEL | /BFH/ACC_DRIVER_VAL3
S4HK900398 | 209 | R3TR | DTEL | /BFH/ACC_DRIVER_VAL4
S4HK900398 | 210 | R3TR | DTEL | /BFH/ACC_DRIVER_VAL5
S4HK900398 | 211 | R3TR | DTEL | /BFH/ACC_DRIVER_VAL6
S4HK900398 | 212 | R3TR | DTEL | /BFH/ACC_DRIVER_VAL7
S4HK900398 | 213 | R3TR | DTEL | /BFH/ACTIVE
S4HK900398 | 214 | R3TR | DTEL | /BFH/ACTIVITY_TYPE
S4HK900398 | 215 | R3TR | DTEL | /BFH/AGNOSTIC_KEY
S4HK900398 | 216 | R3TR | DTEL | /BFH/ALLOC_TEXT1
S4HK900398 | 217 | R3TR | DTEL | /BFH/ALLOC_TEXT2
S4HK900398 | 218 | R3TR | DTEL | /BFH/ALLOC_TEXT3
S4HK900398 | 219 | R3TR | DTEL | /BFH/AMOUNT
S4HK900398 | 220 | R3TR | DTEL | /BFH/AMOUNT_SIGN
S4HK900398 | 221 | R3TR | DTEL | /BFH/AMY_D
S4HK900398 | 222 | R3TR | DTEL | /BFH/BALFV
S4HK900398 | 223 | R3TR | DTEL | /BFH/BET_C
S4HK900398 | 224 | R3TR | DTEL | /BFH/BKPF_BALANCE
S4HK900398 | 225 | R3TR | DTEL | /BFH/BOOKING_PERIOD
S4HK900398 | 226 | R3TR | DTEL | /BFH/BTG
S4HK900398 | 227 | R3TR | DTEL | /BFH/BT_RULE_DESC
S4HK900398 | 228 | R3TR | DTEL | /BFH/BT_RULE_NO
S4HK900398 | 229 | R3TR | DTEL | /BFH/BUCH_D
S4HK900398 | 230 | R3TR | DTEL | /BFH/BUSINESS_RANGE
S4HK900398 | 231 | R3TR | DTEL | /BFH/BUSINESS_UNIT
S4HK900398 | 232 | R3TR | DTEL | /BFH/CALC_RULE_DESC
S4HK900398 | 233 | R3TR | DTEL | /BFH/CALC_RULE_TYP
S4HK900398 | 234 | R3TR | DTEL | /BFH/CALENDAR_ID
S4HK900398 | 235 | R3TR | DTEL | /BFH/CAL_FVT
S4HK900398 | 236 | R3TR | DTEL | /BFH/CHAR50
S4HK900398 | 237 | R3TR | DTEL | /BFH/CHAR76
S4HK900398 | 238 | R3TR | DTEL | /BFH/CHAR_VALUE
S4HK900398 | 239 | R3TR | DTEL | /BFH/CHECKSUM
S4HK900398 | 240 | R3TR | DTEL | /BFH/CLASS_PACKAGE
S4HK900398 | 241 | R3TR | DTEL | /BFH/CLND_DESCR
S4HK900398 | 242 | R3TR | DTEL | /BFH/CODE_PAGE
S4HK900398 | 243 | R3TR | DTEL | /BFH/COLMN_TO_FILTER
S4HK900398 | 244 | R3TR | DTEL | /BFH/COLUMN_DESCR
S4HK900398 | 245 | R3TR | DTEL | /BFH/COLUMN_HEADER_IDENTIFIER
S4HK900398 | 246 | R3TR | DTEL | /BFH/COLUMN_START_END_POSITION
S4HK900398 | 247 | R3TR | DTEL | /BFH/COMMENTS
S4HK900398 | 248 | R3TR | DTEL | /BFH/CONNECTOR_CLASS
S4HK900398 | 249 | R3TR | DTEL | /BFH/CONNECTOR_ID
S4HK900398 | 250 | R3TR | DTEL | /BFH/COST_CENTER
S4HK900398 | 251 | R3TR | DTEL | /BFH/COVERAGE_VALID_FROM_DT
S4HK900398 | 252 | R3TR | DTEL | /BFH/COVERAGE_VALID_TO_DT
S4HK900398 | 253 | R3TR | DTEL | /BFH/COVER_END_DTE
S4HK900398 | 254 | R3TR | DTEL | /BFH/COVER_START_DTE
S4HK900398 | 255 | R3TR | DTEL | /BFH/CO_INSURANCE_COMPANY
S4HK900398 | 256 | R3TR | DTEL | /BFH/CREATED_BY
S4HK900398 | 257 | R3TR | DTEL | /BFH/CREATED_ON
S4HK900398 | 258 | R3TR | DTEL | /BFH/CROSS_SELL_CHECK
S4HK900398 | 259 | R3TR | DTEL | /BFH/CURRENCY_CODE
S4HK900398 | 260 | R3TR | DTEL | /BFH/DATA_ELEMENT_NAME
S4HK900398 | 261 | R3TR | DTEL | /BFH/DATA_LENGTH
S4HK900398 | 262 | R3TR | DTEL | /BFH/DATA_TYPE
S4HK900398 | 263 | R3TR | DTEL | /BFH/DATEYYYYMM
S4HK900398 | 264 | R3TR | DTEL | /BFH/DATE_FORMAT
S4HK900398 | 265 | R3TR | DTEL | /BFH/DEC10_5
S4HK900398 | 266 | R3TR | DTEL | /BFH/DEC13_2
S4HK900398 | 267 | R3TR | DTEL | /BFH/DEC18_2
S4HK900398 | 268 | R3TR | DTEL | /BFH/DEC18_3
S4HK900398 | 269 | R3TR | DTEL | /BFH/DEC18_4
S4HK900398 | 270 | R3TR | DTEL | /BFH/DEC18_6
S4HK900398 | 271 | R3TR | DTEL | /BFH/DEC19_9
S4HK900398 | 272 | R3TR | DTEL | /BFH/DEC3_3
S4HK900398 | 273 | R3TR | DTEL | /BFH/DEC4_2
S4HK900398 | 274 | R3TR | DTEL | /BFH/DEC4_4
S4HK900398 | 275 | R3TR | DTEL | /BFH/DEC6_3
S4HK900398 | 276 | R3TR | DTEL | /BFH/DEC6_4
S4HK900398 | 277 | R3TR | DTEL | /BFH/DECIMAL_FORMAT
S4HK900398 | 278 | R3TR | DTEL | /BFH/DEFAULT_VALUE
S4HK900398 | 279 | R3TR | DTEL | /BFH/DELETE_FLAG
S4HK900398 | 280 | R3TR | DTEL | /BFH/DESCRIPTION
S4HK900398 | 281 | R3TR | DTEL | /BFH/DOCUMENT_COUNT
S4HK900398 | 282 | R3TR | DTEL | /BFH/DRITTE
S4HK900398 | 283 | R3TR | DTEL | /BFH/DRIVER_1
S4HK900398 | 284 | R3TR | DTEL | /BFH/DRIVER_10
S4HK900398 | 285 | R3TR | DTEL | /BFH/DRIVER_2
S4HK900398 | 286 | R3TR | DTEL | /BFH/DRIVER_3
S4HK900398 | 287 | R3TR | DTEL | /BFH/DRIVER_4
S4HK900398 | 288 | R3TR | DTEL | /BFH/DRIVER_5
S4HK900398 | 289 | R3TR | DTEL | /BFH/DRIVER_6
S4HK900398 | 290 | R3TR | DTEL | /BFH/DRIVER_7
S4HK900398 | 291 | R3TR | DTEL | /BFH/DRIVER_8
S4HK900398 | 292 | R3TR | DTEL | /BFH/DRIVER_9
S4HK900398 | 293 | R3TR | DTEL | /BFH/DWH_BT_RULE_DESC
S4HK900398 | 294 | R3TR | DTEL | /BFH/DWH_FILE_TYPE
S4HK900398 | 295 | R3TR | DTEL | /BFH/EM
S4HK900398 | 296 | R3TR | DTEL | /BFH/EM_ID
S4HK900398 | 297 | R3TR | DTEL | /BFH/END_TIMESTAMP
S4HK900398 | 298 | R3TR | DTEL | /BFH/ERROR_ACTION
S4HK900398 | 299 | R3TR | DTEL | /BFH/ERROR_COUNT
S4HK900398 | 300 | R3TR | DTEL | /BFH/ERROR_DATE
S4HK900398 | 301 | R3TR | DTEL | /BFH/ERROR_DEF_1
S4HK900398 | 302 | R3TR | DTEL | /BFH/ERROR_DEF_2
S4HK900398 | 303 | R3TR | DTEL | /BFH/ERROR_LOG_ID
S4HK900398 | 304 | R3TR | DTEL | /BFH/ERROR_MESSAGE
S4HK900398 | 305 | R3TR | DTEL | /BFH/ERROR_ON_COLUMNCOUNT
S4HK900398 | 306 | R3TR | DTEL | /BFH/ERROR_TYP_DESCR
S4HK900398 | 307 | R3TR | DTEL | /BFH/ERR_ID
S4HK900398 | 308 | R3TR | DTEL | /BFH/ERR_TYP
S4HK900398 | 309 | R3TR | DTEL | /BFH/ERR_TYP_ID
S4HK900398 | 310 | R3TR | DTEL | /BFH/ESICHT_1
S4HK900398 | 311 | R3TR | DTEL | /BFH/ESICHT_2
S4HK900398 | 312 | R3TR | DTEL | /BFH/ESICHT_3
S4HK900398 | 313 | R3TR | DTEL | /BFH/EXPRESSION
S4HK900398 | 314 | R3TR | DTEL | /BFH/FDT_FILTER_GROUP_ID
S4HK900398 | 315 | R3TR | DTEL | /BFH/FEG_ID
S4HK900398 | 316 | R3TR | DTEL | /BFH/FIELD
S4HK900398 | 317 | R3TR | DTEL | /BFH/FIELDNAME
S4HK900398 | 318 | R3TR | DTEL | /BFH/FIELD_NAME
S4HK900398 | 319 | R3TR | DTEL | /BFH/FIELD_POSITION
S4HK900398 | 320 | R3TR | DTEL | /BFH/FIELD_STATUS
S4HK900398 | 321 | R3TR | DTEL | /BFH/FILE_ID
S4HK900398 | 322 | R3TR | DTEL | /BFH/FILE_NAME
S4HK900398 | 323 | R3TR | DTEL | /BFH/FILE_PREFIX
S4HK900398 | 324 | R3TR | DTEL | /BFH/FILE_SIZE
S4HK900398 | 325 | R3TR | DTEL | /BFH/FILTER_CONDITION
S4HK900398 | 326 | R3TR | DTEL | /BFH/FILTER_GRP_ID
S4HK900398 | 327 | R3TR | DTEL | /BFH/FILTER_RULE_ID
S4HK900398 | 328 | R3TR | DTEL | /BFH/FILTER_RULE_SET_ID
S4HK900398 | 329 | R3TR | DTEL | /BFH/FILTR_EXP_ID
S4HK900398 | 330 | R3TR | DTEL | /BFH/FIN_TRANSACTION_TYPE
S4HK900398 | 331 | R3TR | DTEL | /BFH/FLTR_EXPRESSION
S4HK900398 | 332 | R3TR | DTEL | /BFH/FLTR_EXPR_ID
S4HK900398 | 333 | R3TR | DTEL | /BFH/FORMAT
S4HK900398 | 334 | R3TR | DTEL | /BFH/FOUNDATION_CODE
S4HK900398 | 335 | R3TR | DTEL | /BFH/FSG
S4HK900398 | 336 | R3TR | DTEL | /BFH/FVT
S4HK900398 | 337 | R3TR | DTEL | /BFH/FVT_ID
S4HK900398 | 338 | R3TR | DTEL | /BFH/FV_ID_CLONED1
S4HK900398 | 339 | R3TR | DTEL | /BFH/FV_ID_CLONED2
S4HK900398 | 340 | R3TR | DTEL | /BFH/FV_ID_CLONED3
S4HK900398 | 341 | R3TR | DTEL | /BFH/GAC_C
S4HK900398 | 342 | R3TR | DTEL | /BFH/GROUP_NAME
S4HK900398 | 343 | R3TR | DTEL | /BFH/HERK_ID
S4HK900398 | 344 | R3TR | DTEL | /BFH/IC_CODE
S4HK900398 | 345 | R3TR | DTEL | /BFH/IDOC_NUM_TARGET_SYS
S4HK900398 | 346 | R3TR | DTEL | /BFH/IDOC_STATUS_TARGET_SYS
S4HK900398 | 347 | R3TR | DTEL | /BFH/IND_3A_3B_C
S4HK900398 | 348 | R3TR | DTEL | /BFH/INFA_COLUMN_NAME
S4HK900398 | 349 | R3TR | DTEL | /BFH/INPUT_FILE_TYPE_DESC
S4HK900398 | 350 | R3TR | DTEL | /BFH/INPUT_FILE_TYPE_NO
S4HK900398 | 351 | R3TR | DTEL | /BFH/INPUT_RULE_NO_KEY
S4HK900398 | 352 | R3TR | DTEL | /BFH/INSURANCE_BENCH
S4HK900398 | 353 | R3TR | DTEL | /BFH/INT2
S4HK900398 | 354 | R3TR | DTEL | /BFH/INT4
S4HK900398 | 355 | R3TR | DTEL | /BFH/INT8
S4HK900398 | 356 | R3TR | DTEL | /BFH/INTERCOMPANY_CODE
S4HK900398 | 357 | R3TR | DTEL | /BFH/INTERFACE_NO
S4HK900398 | 358 | R3TR | DTEL | /BFH/INTERFACE_NUMBER
S4HK900398 | 359 | R3TR | DTEL | /BFH/INTERFACE_NUMBER_ALV
S4HK900398 | 360 | R3TR | DTEL | /BFH/INTERFACE_STATUS
S4HK900398 | 361 | R3TR | DTEL | /BFH/INVALID
S4HK900398 | 362 | R3TR | DTEL | /BFH/IN_ID
S4HK900398 | 363 | R3TR | DTEL | /BFH/ITEMTEXT
S4HK900398 | 364 | R3TR | DTEL | /BFH/ITEMTEXT1
S4HK900398 | 365 | R3TR | DTEL | /BFH/ITEMTEXT2
S4HK900398 | 366 | R3TR | DTEL | /BFH/ITEMTEXT3
S4HK900398 | 367 | R3TR | DTEL | /BFH/ITEMTEXT4
S4HK900398 | 368 | R3TR | DTEL | /BFH/ITEMTEXT5
S4HK900398 | 369 | R3TR | DTEL | /BFH/JUR_C
S4HK900398 | 370 | R3TR | DTEL | /BFH/KOST_NR
S4HK900398 | 371 | R3TR | DTEL | /BFH/LART
S4HK900398 | 372 | R3TR | DTEL | /BFH/LCHAR_1024
S4HK900398 | 373 | R3TR | DTEL | /BFH/LCHAR_516
S4HK900398 | 374 | R3TR | DTEL | /BFH/LEGAL_ENTITY
S4HK900398 | 375 | R3TR | DTEL | /BFH/LEGAL_NON_LEGAL_Q
S4HK900398 | 376 | R3TR | DTEL | /BFH/LENGTH
S4HK900398 | 377 | R3TR | DTEL | /BFH/LEVEL
S4HK900398 | 378 | R3TR | DTEL | /BFH/LINE_ID
S4HK900398 | 379 | R3TR | DTEL | /BFH/LOB_D
S4HK900398 | 380 | R3TR | DTEL | /BFH/LOGDOCNO
S4HK900398 | 381 | R3TR | DTEL | /BFH/LOGITEMNO
S4HK900398 | 382 | R3TR | DTEL | /BFH/LOOKUP
S4HK900398 | 383 | R3TR | DTEL | /BFH/LQ_NLQ_C
S4HK900398 | 384 | R3TR | DTEL | /BFH/MANDATORY
S4HK900398 | 385 | R3TR | DTEL | /BFH/MAN_PROC_FLG
S4HK900398 | 386 | R3TR | DTEL | /BFH/MAPPING_TYPE
S4HK900398 | 387 | R3TR | DTEL | /BFH/MESSAGE_COUNT
S4HK900398 | 388 | R3TR | DTEL | /BFH/MOVFV
S4HK900398 | 389 | R3TR | DTEL | /BFH/MSG_GROUP_DESC
S4HK900398 | 390 | R3TR | DTEL | /BFH/MSG_GROUP_ID
S4HK900398 | 391 | R3TR | DTEL | /BFH/MV_GESELL
S4HK900398 | 392 | R3TR | DTEL | /BFH/NAT_C
S4HK900398 | 393 | R3TR | DTEL | /BFH/NO_OF_DOCS_PER_PROCESS
S4HK900398 | 394 | R3TR | DTEL | /BFH/NUMC6
S4HK900398 | 395 | R3TR | DTEL | /BFH/NUM_VALUE
S4HK900398 | 396 | R3TR | DTEL | /BFH/OCP_C
S4HK900398 | 397 | R3TR | DTEL | /BFH/OUTPUT_TEXT
S4HK900398 | 398 | R3TR | DTEL | /BFH/OUT_ID
S4HK900398 | 399 | R3TR | DTEL | /BFH/PACKAGE_ID_FILE
S4HK900398 | 400 | R3TR | DTEL | /BFH/PACKAGE_ID_NR
S4HK900398 | 401 | R3TR | DTEL | /BFH/PACKAGE_STATUS
S4HK900398 | 402 | R3TR | DTEL | /BFH/PACKED_FORMAT
S4HK900398 | 403 | R3TR | DTEL | /BFH/PARAMETER_NAME
S4HK900398 | 404 | R3TR | DTEL | /BFH/PARAMETER_VALUE
S4HK900398 | 405 | R3TR | DTEL | /BFH/PARAM_NAME
S4HK900398 | 406 | R3TR | DTEL | /BFH/PARAM_VALUE
S4HK900398 | 407 | R3TR | DTEL | /BFH/PENSION_INDICATOR
S4HK900398 | 408 | R3TR | DTEL | /BFH/PERSISTENCE_POLICY
S4HK900398 | 409 | R3TR | DTEL | /BFH/PER_FIRST_DATE
S4HK900398 | 410 | R3TR | DTEL | /BFH/PER_LAST_DATE
S4HK900398 | 411 | R3TR | DTEL | /BFH/PRIM_ACC_TYP
S4HK900398 | 412 | R3TR | DTEL | /BFH/PROCEDURE_NAME
S4HK900398 | 413 | R3TR | DTEL | /BFH/PROCESS_CLASS
S4HK900398 | 414 | R3TR | DTEL | /BFH/PROCESS_DATE
S4HK900398 | 415 | R3TR | DTEL | /BFH/PROCESS_RUN_ID
S4HK900398 | 416 | R3TR | DTEL | /BFH/PROCESS_STATUS
S4HK900398 | 417 | R3TR | DTEL | /BFH/PROCESS_STEP_CLASS
S4HK900398 | 418 | R3TR | DTEL | /BFH/PROCESS_TYPE
S4HK900398 | 419 | R3TR | DTEL | /BFH/PROCESS_TYPE_TEXT
S4HK900398 | 420 | R3TR | DTEL | /BFH/REASON
S4HK900398 | 421 | R3TR | DTEL | /BFH/REASON_CODE
S4HK900398 | 422 | R3TR | DTEL | /BFH/REASON_DESC
S4HK900398 | 423 | R3TR | DTEL | /BFH/RECORD_COUNT
S4HK900398 | 424 | R3TR | DTEL | /BFH/RECORD_IDENTIFIER
S4HK900398 | 425 | R3TR | DTEL | /BFH/RECORD_TYPE
S4HK900398 | 426 | R3TR | DTEL | /BFH/REFRESH_TIMESTAMP
S4HK900398 | 427 | R3TR | DTEL | /BFH/RESULT_HIER_LEVEL_1
S4HK900398 | 428 | R3TR | DTEL | /BFH/RESULT_HIER_LEVEL_2
S4HK900398 | 429 | R3TR | DTEL | /BFH/RESULT_HIER_LEVEL_3
S4HK900398 | 430 | R3TR | DTEL | /BFH/REVERSAL_STATUS
S4HK900398 | 431 | R3TR | DTEL | /BFH/REVERSED
S4HK900398 | 432 | R3TR | DTEL | /BFH/REVERSED_DOC
S4HK900398 | 433 | R3TR | DTEL | /BFH/REVERSED_PKG
S4HK900398 | 434 | R3TR | DTEL | /BFH/REVERSED_STATUS
S4HK900398 | 435 | R3TR | DTEL | /BFH/RE_INSURANCE_CODE
S4HK900398 | 436 | R3TR | DTEL | /BFH/RISIKO
S4HK900398 | 437 | R3TR | DTEL | /BFH/ROLE
S4HK900398 | 438 | R3TR | DTEL | /BFH/ROW_DELIMITER
S4HK900398 | 439 | R3TR | DTEL | /BFH/RULES_VERSION_NO
S4HK900398 | 440 | R3TR | DTEL | /BFH/RULE_END_DATE
S4HK900398 | 441 | R3TR | DTEL | /BFH/RULE_ID
S4HK900398 | 442 | R3TR | DTEL | /BFH/RULE_START_DATE
S4HK900398 | 443 | R3TR | DTEL | /BFH/RUN_TYPE
S4HK900398 | 444 | R3TR | DTEL | /BFH/RV_C
S4HK900398 | 445 | R3TR | DTEL | /BFH/S1_DONT_SIMULATE_POSTING
S4HK900398 | 446 | R3TR | DTEL | /BFH/S1_MAX_PROCS
S4HK900398 | 447 | R3TR | DTEL | /BFH/S1_MAX_UTILIZATION
S4HK900398 | 448 | R3TR | DTEL | /BFH/S1_PARALLEL
S4HK900398 | 449 | R3TR | DTEL | /BFH/S1_PROCESS_SIZE
S4HK900398 | 450 | R3TR | DTEL | /BFH/S1_SERVER_GROUP
S4HK900398 | 451 | R3TR | DTEL | /BFH/S1_SIM_UNTIL_FIRST_ERROR
S4HK900398 | 452 | R3TR | DTEL | /BFH/S2_DONT_SIMULATE_POSTING
S4HK900398 | 453 | R3TR | DTEL | /BFH/S2_MAX_PROCS
S4HK900398 | 454 | R3TR | DTEL | /BFH/S2_MAX_UTILIZATION
S4HK900398 | 455 | R3TR | DTEL | /BFH/S2_PARALLEL
S4HK900398 | 456 | R3TR | DTEL | /BFH/S2_PROCESS_SIZE
S4HK900398 | 457 | R3TR | DTEL | /BFH/S2_SERVER_GROUP
S4HK900398 | 458 | R3TR | DTEL | /BFH/SAP_END_DTE
S4HK900398 | 459 | R3TR | DTEL | /BFH/SAP_HUB_TABLE
S4HK900398 | 460 | R3TR | DTEL | /BFH/SCHD_FIRST_DATE
S4HK900398 | 461 | R3TR | DTEL | /BFH/SCHD_LAST_DATE
S4HK900398 | 462 | R3TR | DTEL | /BFH/SCHEDULE_DATE
S4HK900398 | 463 | R3TR | DTEL | /BFH/SCHED_LAST_DATE
S4HK900398 | 464 | R3TR | DTEL | /BFH/SCH_JJ
S4HK900398 | 465 | R3TR | DTEL | /BFH/SEC_ACC_TYP
S4HK900398 | 466 | R3TR | DTEL | /BFH/SEGMENT_NAME
S4HK900398 | 467 | R3TR | DTEL | /BFH/SELECTION_CRITERIA
S4HK900398 | 468 | R3TR | DTEL | /BFH/SEQUENCE
S4HK900398 | 469 | R3TR | DTEL | /BFH/SIGN
S4HK900398 | 470 | R3TR | DTEL | /BFH/SKIP_HEADER_LINES
S4HK900398 | 471 | R3TR | DTEL | /BFH/SOURCE
S4HK900398 | 472 | R3TR | DTEL | /BFH/SOURCE_FIELD
S4HK900398 | 473 | R3TR | DTEL | /BFH/SOURCE_FILTER_GROUP_ID
S4HK900398 | 474 | R3TR | DTEL | /BFH/SOURCE_RULE_NO
S4HK900398 | 475 | R3TR | DTEL | /BFH/SOURCE_SYSTEM
S4HK900398 | 476 | R3TR | DTEL | /BFH/SOURCE_VALUE_01
S4HK900398 | 477 | R3TR | DTEL | /BFH/SOURCE_VALUE_02
S4HK900398 | 478 | R3TR | DTEL | /BFH/SOURCE_VALUE_03
S4HK900398 | 479 | R3TR | DTEL | /BFH/SOURCE_VALUE_04
S4HK900398 | 480 | R3TR | DTEL | /BFH/SOURCE_VALUE_05
S4HK900398 | 481 | R3TR | DTEL | /BFH/SOURCE_VALUE_06
S4HK900398 | 482 | R3TR | DTEL | /BFH/SOURCE_VALUE_07
S4HK900398 | 483 | R3TR | DTEL | /BFH/SOURCE_VALUE_08
S4HK900398 | 484 | R3TR | DTEL | /BFH/SOURCE_VALUE_09
S4HK900398 | 485 | R3TR | DTEL | /BFH/SOURCE_VALUE_10
S4HK900398 | 486 | R3TR | DTEL | /BFH/SQL_STATEMENT
S4HK900398 | 487 | R3TR | DTEL | /BFH/STAGE
S4HK900398 | 488 | R3TR | DTEL | /BFH/START_POS
S4HK900398 | 489 | R3TR | DTEL | /BFH/START_TIMESTAMP
S4HK900398 | 490 | R3TR | DTEL | /BFH/STATUS_EXTRACT
S4HK900398 | 491 | R3TR | DTEL | /BFH/STATUS_FLAG
S4HK900398 | 492 | R3TR | DTEL | /BFH/STATUS_IDOC
S4HK900398 | 493 | R3TR | DTEL | /BFH/STATUS_LOAD
S4HK900398 | 494 | R3TR | DTEL | /BFH/STATUS_TRANSFORM
S4HK900398 | 495 | R3TR | DTEL | /BFH/STEP_TYPE
S4HK900398 | 496 | R3TR | DTEL | /BFH/STIF_C
S4HK900398 | 497 | R3TR | DTEL | /BFH/STRUCTURE_NAME
S4HK900398 | 498 | R3TR | DTEL | /BFH/SUCCESS_COUNT
S4HK900398 | 499 | R3TR | DTEL | /BFH/SYST_UNAME
S4HK900398 | 500 | R3TR | DTEL | /BFH/TABLE_NAME
S4HK900398 | 501 | R3TR | DTEL | /BFH/TARGET
S4HK900398 | 502 | R3TR | DTEL | /BFH/TARGET_FIELD
S4HK900398 | 503 | R3TR | DTEL | /BFH/TARGET_VALUE_01
S4HK900398 | 504 | R3TR | DTEL | /BFH/TARGET_VALUE_02
S4HK900398 | 505 | R3TR | DTEL | /BFH/TECHNICAL_MESSAGE
S4HK900398 | 506 | R3TR | DTEL | /BFH/TEMPORARY
S4HK900398 | 507 | R3TR | DTEL | /BFH/TEST_MODE
S4HK900398 | 508 | R3TR | DTEL | /BFH/TEXT40
S4HK900398 | 509 | R3TR | DTEL | /BFH/TEXT_LENGTH
S4HK900398 | 510 | R3TR | DTEL | /BFH/TIMESTAMP
S4HK900398 | 511 | R3TR | DTEL | /BFH/TRAD_PRTNR_STAT
S4HK900398 | 512 | R3TR | DTEL | /BFH/TRAFFIC_STATUS
S4HK900398 | 513 | R3TR | DTEL | /BFH/TYPE_OF_BUSINESS
S4HK900398 | 514 | R3TR | DTEL | /BFH/TYPE_OF_POSTING
S4HK900398 | 515 | R3TR | DTEL | /BFH/UNION_VIEW_NAME
S4HK900398 | 516 | R3TR | DTEL | /BFH/UPDATED_BY
S4HK900398 | 517 | R3TR | DTEL | /BFH/UPDATED_ON
S4HK900398 | 518 | R3TR | DTEL | /BFH/VALID_FROM
S4HK900398 | 519 | R3TR | DTEL | /BFH/VALID_TO
S4HK900398 | 520 | R3TR | DTEL | /BFH/VALUE1
S4HK900398 | 521 | R3TR | DTEL | /BFH/VALUE2
S4HK900398 | 522 | R3TR | DTEL | /BFH/VALUE3
S4HK900398 | 523 | R3TR | DTEL | /BFH/VALUE4
S4HK900398 | 524 | R3TR | DTEL | /BFH/VALUE_FROM
S4HK900398 | 525 | R3TR | DTEL | /BFH/VALUE_ID
S4HK900398 | 526 | R3TR | DTEL | /BFH/VALUE_TO
S4HK900398 | 527 | R3TR | DTEL | /BFH/VZ4_C
S4HK900398 | 528 | R3TR | DTEL | /BFH/WARN_COUNT
S4HK900398 | 529 | R3TR | DTEL | /BFH/WHERE_CLAUSE
S4HK900398 | 530 | R3TR | DTEL | /BFH/WHRG_C
S4HK900398 | 531 | R3TR | DTEL | /BFH/XUDATFM
S4HK900398 | 532 | R3TR | FUGR | /BFH/EM_HEADER
S4HK900398 | 533 | R3TR | FUGR | /BFH/EM_TABFIELD
S4HK900398 | 534 | R3TR | FUGR | /BFH/ITF_MSG_DEF
S4HK900398 | 535 | R3TR | FUGR | /BFH/MSG_GROUP
S4HK900398 | 536 | R3TR | FUGR | /BFH/MSG_GROUP_D
S4HK900398 | 537 | R3TR | NROB | /BFH/EMID
S4HK900398 | 538 | R3TR | NROB | /BFH/MGPID
S4HK900398 | 539 | R3TR | TABL | /BFH/PARAM_VAL
S4HK900398 | 540 | R3TR | PROG | /BFH/INTERFACE_COCKPIT_UI_EVT
S4HK900398 | 541 | R3TR | PROG | /BFH/INTERFACE_COCKPIT_UI_F01
S4HK900398 | 542 | R3TR | PROG | /BFH/INTERFACE_COCKPIT_UI_SEL
S4HK900398 | 543 | R3TR | PROG | /BFH/INTERFACE_COCKPIT_UI_TOP
S4HK900398 | 544 | R3TR | PROG | /BFH/MONITOR_COCKPIT_UI
S4HK900398 | 545 | R3TR | SHLP | /BFH/SH_EM_TABFIELD
S4HK900398 | 546 | R3TR | SHLP | /BFH/SH_EM_TABLE
S4HK900398 | 547 | R3TR | SHLP | /BFH/SH_INTERFACE_NUMBER
S4HK900398 | 548 | R3TR | SHLP | /BFH/SH_INTERFACE_STATUS
S4HK900398 | 549 | R3TR | SHLP | /BFH/SH_REV_REASON
S4HK900398 | 550 | R3TR | TABL | /BFH/ACC_DOCUMENT_MESSAGES
S4HK900398 | 551 | R3TR | TABL | /BFH/CHECK_TABLE
S4HK900398 | 552 | R3TR | TABL | /BFH/CONNECTION
S4HK900398 | 553 | R3TR | TABL | /BFH/CONNECTOR
S4HK900398 | 554 | R3TR | TABL | /BFH/CONN_PARAMS
S4HK900398 | 555 | R3TR | TABL | /BFH/EM_ITEM
S4HK900398 | 556 | R3TR | TABL | /BFH/EM_TABFIELD
S4HK900398 | 557 | R3TR | TABL | /BFH/ENVI_PARAMS
S4HK900398 | 558 | R3TR | TABL | /BFH/ERRORHDL_ALV
S4HK900398 | 559 | R3TR | TABL | /BFH/ERRORHDL_ENH_ALV
S4HK900398 | 560 | R3TR | TABL | /BFH/ERROR_TYPES
S4HK900398 | 561 | R3TR | TABL | /BFH/FLTR_G_ASOC
S4HK900398 | 562 | R3TR | TABL | /BFH/FLTR_RULE
S4HK900398 | 563 | R3TR | TABL | /BFH/FLTR_R_DET
S4HK900398 | 564 | R3TR | TABL | /BFH/FLTR_R_SET
S4HK900398 | 565 | R3TR | TABL | /BFH/HUB_REASON
S4HK900398 | 566 | R3TR | TABL | /BFH/I2_BETRAGS
S4HK900398 | 567 | R3TR | TABL | /BFH/INBOUND
S4HK900398 | 568 | R3TR | TABL | /BFH/INT_PARAM
S4HK900398 | 569 | R3TR | TABL | /BFH/ITF_MSG_DEF
S4HK900398 | 570 | R3TR | TABL | /BFH/I_CAL_RUL
S4HK900398 | 571 | R3TR | TABL | /BFH/I_CLONCTRL
S4HK900398 | 572 | R3TR | TABL | /BFH/I_FLTR_EXPR
S4HK900398 | 573 | R3TR | TABL | /BFH/I_FSTAG
S4HK900398 | 574 | R3TR | TABL | /BFH/I_F_VAL_DER
S4HK900398 | 575 | R3TR | DTEL | /BFH/IS_RUNTIME
S4HK900398 | 576 | R3TR | TABL | /BFH/I_PERMAN
S4HK900398 | 577 | R3TR | TABL | /BFH/LKP_DRIVERS
S4HK900398 | 578 | R3TR | TABL | /BFH/LKP_VALUES
S4HK900398 | 579 | R3TR | TABL | /BFH/MAPPING
S4HK900398 | 580 | R3TR | TABL | /BFH/MASTDTA_VAL
S4HK900398 | 581 | R3TR | TABL | /BFH/MONITOR_COCKPIT_ALV
S4HK900398 | 582 | R3TR | TABL | /BFH/MSG_GROUP
S4HK900398 | 583 | R3TR | TABL | /BFH/MSG_GROUP_D
S4HK900398 | 584 | R3TR | TABL | /BFH/OUTBOUND
S4HK900398 | 585 | R3TR | TABL | /BFH/PARALLEL_SETTINGS
S4HK900398 | 586 | R3TR | TABL | /BFH/REVERSAL_UI
S4HK900398 | 587 | R3TR | TABL | /BFH/REV_PACKAGE
S4HK900398 | 588 | R3TR | TABL | /BFH/REV_PACKAGE_DOC_OUT
S4HK900398 | 589 | R3TR | TABL | /BFH/RNG_BUSINESS_UNIT
S4HK900398 | 590 | R3TR | TABL | /BFH/RNG_INTERFACE_NAME
S4HK900398 | 591 | R3TR | TABL | /BFH/RNG_INTERFACE_NUM
S4HK900398 | 592 | R3TR | TABL | /BFH/RNG_PACKAGE_ID
S4HK900398 | 593 | R3TR | TABL | /BFH/S1_BKPF
S4HK900398 | 594 | R3TR | TABL | /BFH/STRUCTURE
S4HK900398 | 595 | R3TR | TABL | /BFH/ST_AUDIT
S4HK900398 | 596 | R3TR | TABL | /BFH/ST_BBKPF_ZFIELDS
S4HK900398 | 597 | R3TR | TABL | /BFH/ST_BKPF
S4HK900398 | 598 | R3TR | TABL | /BFH/ST_DATA_FIELD
S4HK900398 | 599 | R3TR | TABL | /BFH/ST_DATA_SEGMENT
S4HK900398 | 600 | R3TR | TABL | /BFH/ST_ERROR_SET
S4HK900398 | 601 | R3TR | TABL | /BFH/ST_FILE_FLD_POS
S4HK900398 | 602 | R3TR | TABL | /BFH/ST_FLATFILE_SEGMENT
S4HK900398 | 603 | R3TR | TABL | /BFH/ST_STRING
S4HK900398 | 604 | R3TR | TABL | /BFH/ST_VALIDITY
S4HK900398 | 605 | R3TR | TABL | /BFH/TEMP_FILTER
S4HK900398 | 606 | R3TR | TOBJ | /BFH/CHECK_TABLES
S4HK900398 | 607 | R3TR | TOBJ | /BFH/CONNECTORS
S4HK900398 | 608 | R3TR | TOBJ | /BFH/CONN_PARAMSS
S4HK900398 | 609 | R3TR | TOBJ | /BFH/DATA_FIELDS
S4HK900398 | 610 | R3TR | TOBJ | /BFH/EM_HEADERS
S4HK900398 | 611 | R3TR | TOBJ | /BFH/EM_TABFIELDS
S4HK900398 | 612 | R3TR | TOBJ | /BFH/ENVI_PARAMSS
S4HK900398 | 613 | R3TR | TOBJ | /BFH/ERROR_TYPESS
S4HK900398 | 614 | R3TR | TOBJ | /BFH/ERR_MASTERS
S4HK900398 | 615 | R3TR | TOBJ | /BFH/FLTR_GRPS
S4HK900398 | 616 | R3TR | TOBJ | /BFH/FLTR_G_ASOCS
S4HK900398 | 617 | R3TR | TOBJ | /BFH/FLTR_RULES
S4HK900398 | 618 | R3TR | TOBJ | /BFH/FLTR_R_DETS
S4HK900398 | 619 | R3TR | TOBJ | /BFH/FLTR_R_SETS
S4HK900398 | 620 | R3TR | TOBJ | /BFH/HUB_REASONS
S4HK900398 | 621 | R3TR | TOBJ | /BFH/INBOUNDS
S4HK900398 | 622 | R3TR | TOBJ | /BFH/INT_PARAMS
S4HK900398 | 623 | R3TR | TOBJ | /BFH/INT_POSTS
S4HK900398 | 624 | R3TR | TOBJ | /BFH/ITF_MSG_DEFS
S4HK900398 | 625 | R3TR | TOBJ | /BFH/I_F_VAL_DERS
S4HK900398 | 626 | R3TR | TOBJ | /BFH/MAPPINGS
S4HK900398 | 627 | R3TR | TOBJ | /BFH/MASTDTA_VALS
S4HK900398 | 628 | R3TR | TOBJ | /BFH/MSG_GROUPS
S4HK900398 | 629 | R3TR | TOBJ | /BFH/MSG_GROUP_DS
S4HK900398 | 630 | R3TR | TOBJ | /BFH/OUTBOUNDS
S4HK900398 | 631 | R3TR | TOBJ | /BFH/PROCESSSTEPS
S4HK900398 | 632 | R3TR | TOBJ | /BFH/RUN_LOG_IFS
S4HK900398 | 633 | R3TR | TRAN | /BFH/NR_PACKAGE_ID
S4HK900398 | 634 | R3TR | TTYP | /BFH/ACC_DOCUMENT_MESSAGES_TT
S4HK900398 | 635 | R3TR | TTYP | /BFH/ACC_DOCUMENT_TT
S4HK900398 | 636 | R3TR | TTYP | /BFH/TT_BAPI_ERROR_SET
S4HK900398 | 637 | R3TR | TTYP | /BFH/TT_BAPI_RET
S4HK900398 | 638 | R3TR | TTYP | /BFH/TT_CONN_PARAMS
S4HK900398 | 639 | R3TR | TTYP | /BFH/TT_DATA_FIELD
S4HK900398 | 640 | R3TR | TTYP | /BFH/TT_DATA_FIELD_PROPS
S4HK900398 | 641 | R3TR | TTYP | /BFH/TT_DATA_SEGMENTS
S4HK900398 | 642 | R3TR | TTYP | /BFH/TT_DIRFILELIST
S4HK900398 | 643 | R3TR | TTYP | /BFH/TT_ERROR_SET
S4HK900398 | 644 | R3TR | TTYP | /BFH/TT_FILE_FLD_POS
S4HK900398 | 645 | R3TR | TTYP | /BFH/TT_FLATFILE_SEGMENT
S4HK900398 | 646 | R3TR | TTYP | /BFH/TT_FREE_TEXT_ERROR_SET
S4HK900398 | 647 | R3TR | TTYP | /BFH/TT_INBOUND
S4HK900398 | 648 | R3TR | TTYP | /BFH/TT_INT_PARAMS
S4HK900398 | 649 | R3TR | TTYP | /BFH/TT_STRING
S4HK900398 | 650 | R3TR | TTYP | /BFH/T_ERRORHDL_ALV
S4HK900398 | 651 | R3TR | TTYP | /BFH/T_ERRORHDL_ENH_ALV
S4HK900398 | 652 | R3TR | TTYP | /BFH/T_ERROR_LOG
S4HK900398 | 653 | R3TR | TTYP | /BFH/T_INTERFACE_NUMBER
S4HK900398 | 654 | R3TR | TTYP | /BFH/T_MONITOR_COCKPIT_ALV
S4HK900398 | 655 | R3TR | TTYP | /BFH/T_RNG_BUSINESS_UNIT
S4HK900398 | 656 | R3TR | TTYP | /BFH/T_RNG_INTERFACE_NAME
S4HK900398 | 657 | R3TR | TTYP | /BFH/T_RNG_INTERFACE_NUM
S4HK900398 | 658 | R3TR | TTYP | /BFH/T_RNG_PACKAGE_ID
S4HK900398 | 659 | R3TR | TABL | /BFH/ST_FIXEDLENGTH_CONNECTOR
S4HK900398 | 660 | R3TR | TABL | /BFH/ST_CONNECTOR
S4HK900398 | 661 | R3TR | TABL | /BFH/ST_FLATFILE_CONNECTOR
S4HK900398 | 662 | R3TR | CLAS | /BFH/CL_DPD_APP_MOD
S4HK900398 | 663 | R3TR | TABL | /BFH/ST_PROCESS_STEP
S4HK900398 | 664 | R3TR | TABL | /BFH/ERR_MASTER
S4HK900398 | 665 | R3TR | TABL | /BFH/FLTR_GRP
S4HK900398 | 666 | R3TR | TABL | /BFH/INT_POST
S4HK900398 | 667 | R3TR | TOBJ | /BFH/PROC_STEPS
S4HK900398 | 668 | R3TR | DTEL | /BFH/POSTING_DATE
S4HK900398 | 669 | R3TR | DDLS | /BFH/CALCULATION_STORE
S4HK900398 | 670 | R3TR | DDLS | /BFH/FSG
S4HK900398 | 671 | R3TR | DDLS | /BFH/TCNORMALFSG
S4HK900398 | 672 | R3TR | DDLS | /BFH/TCNORMALFSG1
S4HK900398 | 673 | R3TR | DTEL | /BFH/EXECUTION_DATE
S4HK900398 | 674 | R3TR | DDLS | /BFH/TMODU
S4HK900398 | 675 | R3TR | TABL | /BFH/EMER_MAPDEF
S4HK900398 | 676 | R3TR | DTEL | /BFH/EMERGENCY_MAPID
S4HK900398 | 677 | R3TR | DTEL | /BFH/EXECUTION_ON
S4HK900398 | 678 | R3TR | DTEL | /BFH/EXECUTED_BY
S4HK900398 | 679 | R3TR | DDLS | /BFH/TTNORMALFSG
S4HK900398 | 680 | R3TR | DDLS | /BFH/XCERROR_LOG
S4HK900398 | 681 | R3TR | DOMA | /BFH/ACCOUNT_TYPE
S4HK900398 | 682 | R3TR | DOMA | /BFH/AGG_LOG
S4HK900398 | 683 | R3TR | DOMA | /BFH/AGG_RULE_TYPE
S4HK900398 | 684 | R3TR | DOMA | /BFH/CHAR47
S4HK900398 | 685 | R3TR | DOMA | /BFH/CONNECTION_ID
S4HK900398 | 686 | R3TR | DOMA | /BFH/DEC11_2
S4HK900398 | 687 | R3TR | DOMA | /BFH/EXCEPTION_RULE_ID
S4HK900398 | 688 | R3TR | DOMA | /BFH/HDT
S4HK900398 | 689 | R3TR | DOMA | /BFH/LINE_ID_NUMC
S4HK900398 | 690 | R3TR | DOMA | /BFH/LOGITEMNO
S4HK900398 | 691 | R3TR | DOMA | /BFH/MEMORY_SIZE
S4HK900398 | 692 | R3TR | DOMA | /BFH/POSTT
S4HK900398 | 693 | R3TR | DOMA | /BFH/PREMT
S4HK900398 | 694 | R3TR | DOMA | /BFH/PROCESS_ID
S4HK900398 | 695 | R3TR | DOMA | /BFH/PROCESS_TYPE
S4HK900398 | 696 | R3TR | DOMA | /BFH/RAG
S4HK900398 | 697 | R3TR | DOMA | /BFH/S1_AGG_FIELD
S4HK900398 | 698 | R3TR | DOMA | /BFH/S2_AGG_TYPE
S4HK900398 | 699 | R3TR | DOMA | /BFH/SEG_TYPE
S4HK900398 | 700 | R3TR | DOMA | /BFH/SIMULATE_POSTING
S4HK900398 | 701 | R3TR | DOMA | /BFH/STRUCTURE_NAME
S4HK900398 | 702 | R3TR | TABL | /BFH/TMP_FLTR
S4HK900398 | 703 | R3TR | DOMA | /BFH/TARGET_VALUE
S4HK900398 | 704 | R3TR | DOMA | /BFH/TRANSACTION_ID
S4HK900398 | 705 | R3TR | DOMA | /BFH/VMULT
S4HK900398 | 706 | R3TR | DOMA | /BFH/YN_FLAG
S4HK900398 | 707 | R3TR | DTEL | /BFH/ACCOUNT_TYPE
S4HK900398 | 708 | R3TR | DTEL | /BFH/SIMULATE_OR_POST
S4HK900398 | 709 | R3TR | DOMA | /BFH/SIMULATE_OR_POST
S4HK900398 | 710 | R3TR | DTEL | /BFH/ACC_FROM
S4HK900398 | 711 | R3TR | DTEL | /BFH/ACC_TO
S4HK900398 | 712 | R3TR | TABL | /BFH/ROLE_ASSIG
S4HK900398 | 713 | R3TR | DTEL | /BFH/AGG_FLAG
S4HK900398 | 714 | R3TR | DTEL | /BFH/AGG_LOG
S4HK900398 | 715 | R3TR | DDLS | /BFH/ERROR_LOG_MASTER
S4HK900398 | 716 | R3TR | DTEL | /BFH/AGG_RULE_TYPE
S4HK900398 | 717 | R3TR | DTEL | /BFH/ALLOCATION_FLAG
S4HK900398 | 718 | R3TR | DTEL | /BFH/ALLOC_MEMORY_SIZE
S4HK900398 | 719 | R3TR | DTEL | /BFH/APPLICATION_SOURCE
S4HK900398 | 720 | R3TR | DTEL | /BFH/CHAR47
S4HK900398 | 721 | R3TR | DTEL | /BFH/CLOSE_DATE
S4HK900398 | 722 | R3TR | DTEL | /BFH/CONNECTION_ID
S4HK900398 | 723 | R3TR | DTEL | /BFH/DDIC_NAME
S4HK900398 | 724 | R3TR | DTEL | /BFH/DEC11_2
S4HK900398 | 725 | R3TR | DTEL | /BFH/DURATION_SEC
S4HK900398 | 726 | R3TR | DTEL | /BFH/EARNED_MONTHS
S4HK900398 | 727 | R3TR | DTEL | /BFH/EARNED_YEARS
S4HK900398 | 728 | R3TR | DTEL | /BFH/EXCEPTION_RULE_ID
S4HK900398 | 729 | R3TR | DTEL | /BFH/FILE_POS_CNT
S4HK900398 | 730 | R3TR | DTEL | /BFH/FLAT_FLAG
S4HK900398 | 731 | R3TR | DTEL | /BFH/HDT
S4HK900398 | 732 | R3TR | DTEL | /BFH/INTERFACE_NAME
S4HK900398 | 733 | R3TR | DTEL | /BFH/LAYER_ID
S4HK900398 | 734 | R3TR | DTEL | /BFH/LINE_ID_NUMC
S4HK900398 | 735 | R3TR | DTEL | /BFH/MEMORY_SIZE
S4HK900398 | 736 | R3TR | DTEL | /BFH/PACKAGE_ID
S4HK900398 | 737 | R3TR | DTEL | /BFH/PDA_FLAG
S4HK900398 | 738 | R3TR | DTEL | /BFH/POSTING_TEXT_FLAG
S4HK900398 | 739 | R3TR | DTEL | /BFH/POSTT
S4HK900398 | 740 | R3TR | DTEL | /BFH/PREMT
S4HK900398 | 741 | R3TR | DTEL | /BFH/PROCESS_ID
S4HK900398 | 742 | R3TR | DTEL | /BFH/PROCESS_STEP_ID
S4HK900398 | 743 | R3TR | DTEL | /BFH/RAG
S4HK900398 | 744 | R3TR | DTEL | /BFH/RUN_LINE_ID
S4HK900398 | 745 | R3TR | DTEL | /BFH/RUN_PACKAGE_ID
S4HK900398 | 746 | R3TR | DTEL | /BFH/S1_AGG_FIELD
S4HK900398 | 747 | R3TR | DTEL | /BFH/S1_SIMULATE_POSTING
S4HK900398 | 748 | R3TR | DTEL | /BFH/S2_AGG_GROUP_ID
S4HK900398 | 749 | R3TR | DTEL | /BFH/S2_AGG_SGTXT
S4HK900398 | 750 | R3TR | DTEL | /BFH/S2_AGG_TYPE
S4HK900398 | 751 | R3TR | DTEL | /BFH/S2_AGG_ZUONR
S4HK900398 | 752 | R3TR | DTEL | /BFH/SEG_TYPE
S4HK900398 | 753 | R3TR | DTEL | /BFH/SKIP_GENERATION
S4HK900398 | 754 | R3TR | DTEL | /BFH/START_DATE
S4HK900398 | 755 | R3TR | DTEL | /BFH/STATEMENT_ID
S4HK900398 | 756 | R3TR | DTEL | /BFH/STATEMENT_STRING
S4HK900398 | 757 | R3TR | DTEL | /BFH/STEP_ID
S4HK900398 | 758 | R3TR | DTEL | /BFH/TERM
S4HK900398 | 759 | R3TR | DTEL | /BFH/TERMC
S4HK900398 | 760 | R3TR | DTEL | /BFH/TERMMX
S4HK900398 | 761 | R3TR | DTEL | /BFH/TERMY
S4HK900398 | 762 | R3TR | DTEL | /BFH/TERM_LENGTH
S4HK900398 | 763 | R3TR | DTEL | /BFH/TRANSACTION_ID
S4HK900398 | 764 | R3TR | DTEL | /BFH/VMULT
S4HK900398 | 765 | R3TR | FUGR | /BFH/DATA_MAINT
S4HK900398 | 766 | R3TR | NROB | /BFH/PKGID
S4HK900398 | 767 | R3TR | NROB | /BFH/SEGID
S4HK900398 | 768 | R3TR | SHLP | /BFH/SH_INTERFACE
S4HK900398 | 769 | R3TR | SHLP | /BFH/SH_PACKAGE
S4HK900398 | 770 | R3TR | SHLP | /BFH/SH_PROCESS
S4HK900398 | 771 | R3TR | TABL | /BFH/ACC_DOCUMENT
S4HK900398 | 772 | R3TR | TABL | /BFH/DATA_FIELD
S4HK900398 | 773 | R3TR | TABL | /BFH/DATA_SEGMNT
S4HK900398 | 774 | R3TR | TABL | /BFH/EM_HEADER
S4HK900398 | 775 | R3TR | TABL | /BFH/ERROR_LOG
S4HK900398 | 776 | R3TR | TABL | /BFH/INTERFACE
S4HK900398 | 777 | R3TR | TABL | /BFH/I_AGG_RULES
S4HK900398 | 778 | R3TR | TABL | /BFH/I_VAL_MD
S4HK900398 | 779 | R3TR | TABL | /BFH/MSG_LOG
S4HK900398 | 780 | R3TR | TABL | /BFH/MSG_MASTER
S4HK900398 | 781 | R3TR | TABL | /BFH/POLICY
S4HK900398 | 782 | R3TR | TABL | /BFH/PROCESS
S4HK900398 | 783 | R3TR | TABL | /BFH/S1_BSEG
S4HK900398 | 784 | R3TR | TABL | /BFH/STEP
S4HK900398 | 785 | R3TR | TABL | /BFH/ST_BAPI_ERROR_SET
S4HK900398 | 786 | R3TR | TABL | /BFH/ST_BAPI_RET
S4HK900398 | 787 | R3TR | TABL | /BFH/ST_BSEG
S4HK900398 | 788 | R3TR | TABL | /BFH/ST_CSV_CONNECTOR
S4HK900398 | 789 | R3TR | TABL | /BFH/ST_FLD_POSITIONS
S4HK900398 | 790 | R3TR | TABL | /BFH/ST_FREE_TEXT_ERROR_SET
S4HK900398 | 791 | R3TR | DOMA | /BFH/POSTING_DATE
S4HK900398 | 792 | R3TR | DTEL | /BFH/POSTING_AMOUNT
S4HK900398 | 793 | R3TR | DOMA | /BFH/POSTING_AMOUNT
S4HK900398 | 794 | R3TR | TABL | /BFH/T
S4HK900398 | 795 | R3TR | TABL | /BFH/TRACEBILITY
S4HK900398 | 796 | R3TR | TABL | /BFH/VALIDATION
S4HK900398 | 797 | R3TR | TOBJ | /BFH/CONNECTIONS
S4HK900398 | 798 | R3TR | TOBJ | /BFH/DATA_SEGMNTS
S4HK900398 | 799 | R3TR | TOBJ | /BFH/INTERFACES
S4HK900398 | 800 | R3TR | TOBJ | /BFH/I_AGG_RULESS
S4HK900398 | 801 | R3TR | TOBJ | /BFH/I_VAL_MDS
S4HK900398 | 802 | R3TR | TOBJ | /BFH/LKP_DRIVERSS
S4HK900398 | 803 | R3TR | TOBJ | /BFH/LKP_VALUESS
S4HK900398 | 804 | R3TR | TOBJ | /BFH/LOAD_TABLESS
S4HK900398 | 805 | R3TR | TOBJ | /BFH/POLICYS
S4HK900398 | 806 | R3TR | TOBJ | /BFH/PROCESSS
S4HK900398 | 807 | R3TR | TOBJ | /BFH/STEP S
S4HK900398 | 808 | R3TR | TOBJ | /BFH/STRUCTURES
S4HK900398 | 809 | R3TR | TOBJ | /BFH/TEMP_FILTERS
S4HK900398 | 810 | R3TR | TOBJ | /BFH/VALIDATIONS
S4HK900398 | 811 | R3TR | TRAN | /BFH/NR_SEGMENT_ID
S4HK900398 | 812 | R3TR | DOMA | /BFH/SOURCE_VALUE
S4HK900398 | 813 | R3TR | DOMA | /BFH/STEP_TYPE
S4HK900398 | 814 | R3TR | SHLP | /BFH/SH_STEP_ID
S4HK900398 | 815 | R3TR | FUGR | /BFH/BALA_INB_TABLE_LOAD
S4HK900398 | 816 | R3TR | SOTR | /BFH/DATA_FOUNDATION
S4HK900398 | 817 | R3TR | DTEL | /BFH/SEQUENCE_NO
S4HK900398 | 818 | R3TR | DOMA | /BFH/TAB_NAME
S4HK900398 | 819 | R3TR | DTEL | /BFH/TAB_NAME
S4HK900398 | 820 | R3TR | DTEL | /BFH/TABL_NAME
S4HK900398 | 821 | R3TR | TABL | /BFH/LOAD_TABLES
S4HK900398 | 822 | R3TR | TABL | /BFH/ST_LOAD_TABLES
S4HK900398 | 823 | R3TR | TTYP | /BFH/TT_LOAD_TABLES
S4HK900398 | 824 | R3TR | TTYP | /BFH/TT_PACKAGE_ID
S4HK900398 | 825 | R3TR | DOMA | /BFH/MAPPING_TYPE
S4HK900398 | 826 | R3TR | DTEL | /BFH/POLICY_NO
S4HK900398 | 827 | R3TR | TABL | /BFH/CALC_STORE
S4HK900398 | 828 | R3TR | DTEL | /BFH/PACKAGE_NAME
S4HK900398 | 829 | R3TR | DOMA | /BFH/SEGMENT_ID_NR
S4HK900398 | 830 | R3TR | DTEL | /BFH/SEGMENT_ID_NR
S4HK900398 | 831 | R3TR | DOMA | /BFH/MESSAGE
S4HK900398 | 832 | R3TR | DOMA | /BFH/MESSAGE_CLASS
S4HK900398 | 833 | R3TR | DTEL | /BFH/MESSAGE
S4HK900398 | 834 | R3TR | DTEL | /BFH/MESSAGE_CLASS
S4HK900398 | 835 | R3TR | INTF | /BFH/IF_DPD_TREE_OBJECT
S4HK900398 | 836 | R3TR | TTYP | /BFH/TT_LINE_ID
S4HK900398 | 837 | R3TR | TOBJ | /BFH/MSG_MASTERS
S4HK900398 | 838 | R3TR | TABL | /BFH/PROC_STEP
S4HK900398 | 839 | R3TR | TABL | /BFH/IF_PROCESS
S4HK900398 | 840 | R3TR | TABL | /BFH/SQL_LOG
S4HK900398 | 841 | R3TR | TABL | /BFH/I_PSVALUES
S4HK900398 | 842 | R3TR | TABL | /BFH/I_PSDRIVERS
S4HK900398 | 843 | R3TR | TABL | /BFH/IF_LOG
S4HK900398 | 844 | R3TR | TABL | /BFH/PROCESS_LOG
S4HK900398 | 845 | R3TR | TABL | /BFH/STEP_LOG
S4HK900398 | 846 | R3TR | DTEL | /BFH/PROJECT_ID
S4HK900398 | 847 | R3TR | DOMA | /BFH/PROJECT_ID
S4HK900398 | 848 | R3TR | DTEL | /BFH/SUBPROJECT_ID
S4HK900398 | 849 | R3TR | DOMA | /BFH/SUBPROJECT_ID
S4HK900398 | 850 | R3TR | TOBJ | /BFH/IF_PROCESSS
S4HK900398 | 851 | R3TR | TABL | /BFH/I_LDGRGRP
S4HK900398 | 852 | R3TR | TABL | /BFH/RULE_REFRSH
S4HK900398 | 853 | R3TR | TABL | /BFH/S1_BBKPF
S4HK900398 | 854 | R3TR | TABL | /BFH/S1_BBSEG
S4HK900398 | 855 | R3TR | TABL | /BFH/TEST
S4HK900398 | 856 | R3TR | TTYP | /BFH/TT_RUN_PACKAGE_ID
S4HK900398 | 857 | R3TR | TTYP | /BFH/TT_RUN_LINE_ID
S4HK900398 | 858 | R3TR | TABL | /BFH/CALC_RULE
S4HK900398 | 859 | R3TR | TABL | /BFH/ST_FREE_TEXT_MESSAGE_SET
S4HK900398 | 860 | R3TR | TTYP | /BFH/TT_FREE_TEXT_MESSAGE_SET
S4HK900398 | 861 | R3TR | TABL | /BFH/ST_BAPI_MESSAGE_SET
S4HK900398 | 862 | R3TR | TTYP | /BFH/TT_BAPI_MESSAGE_SET
S4HK900398 | 863 | R3TR | TABL | /BFH/ST_MESSAGE_SET
S4HK900398 | 864 | R3TR | TTYP | /BFH/TT_MESSAGE_SET
S4HK900398 | 865 | R3TR | DTEL | /BFH/MESSAGE_CATEGORY
S4HK900398 | 866 | R3TR | DOMA | /BFH/MESSAGE_CATEGORY
S4HK900398 | 867 | R3TR | TOBJ | /BFH/PARAM_VALS
S4HK900398 | 868 | R3TR | DDLS | /BFH/ACDOCA1
S4HK900398 | 869 | R3TR | DDLS | /BFH/ACDOCA2
S4HK900398 | 870 | R3TR | TABL | /BFH/POST_MATRIX
S4HK900398 | 871 | R3TR | DTEL | /BFH/ORDER
S4HK900398 | 872 | R3TR | DOMA | /BFH/ORDER
S4HK900398 | 873 | R3TR | DTEL | /BFH/POSTING_ID
S4HK900398 | 874 | R3TR | DOMA | /BFH/POSTING_ID
S4HK900398 | 875 | R3TR | DTEL | /BFH/POSTING_DESCR
S4HK900398 | 876 | R3TR | DOMA | /BFH/POSTING_DESCR
S4HK900398 | 877 | R3TR | TOBJ | /BFH/POST_MATRIXS
S4HK900398 | 878 | R3TR | DTEL | /BFH/CHECK_FIELD1
S4HK900398 | 879 | R3TR | DTEL | /BFH/CHECK_FIELD2
S4HK900398 | 880 | R3TR | DTEL | /BFH/CHECK_FIELD3
S4HK900398 | 881 | R3TR | DTEL | /BFH/DIM_FIELD1
S4HK900398 | 882 | R3TR | DTEL | /BFH/DIM_FIELD2
S4HK900398 | 883 | R3TR | DTEL | /BFH/DIM_FIELD3
S4HK900398 | 884 | R3TR | DTEL | /BFH/DIM_TABLE
S4HK900398 | 885 | R3TR | DTEL | /BFH/CHECK_TABLE_DE
S4HK900398 | 886 | R3TR | DTEL | /BFH/TEST_STRING
S4HK900398 | 887 | R3TR | TABL | /BFH/EXPRESSIONS
S4HK900398 | 888 | R3TR | DTEL | /BFH/EXPRESSION_ID
S4HK900398 | 889 | R3TR | DOMA | /BFH/EXPRESSION_ID
S4HK900398 | 890 | R3TR | DDLS | /BFH/PROCESS_STEP
S4HK900398 | 891 | R3TR | SHLP | /BFH/SH_STEP
S4HK900398 | 892 | R3TR | FUGR | /BFH/I_F_VAL_DER
S4HK900398 | 893 | R3TR | TTYP | /BFH/TT_STEP_ID
S4HK900398 | 894 | R3TR | DTEL | /BFH/AMOUNT_EXPRESSION
S4HK900398 | 895 | R3TR | DTEL | /BFH/DATE_EXPRESSION
S4HK900398 | 896 | R3TR | DTEL | /BFH/RETAIN_SIGN
S4HK900398 | 897 | R3TR | DOMA | /BFH/SHA256HASH
S4HK900398 | 898 | R3TR | DTEL | /BFH/SHA256HASH
S4HK900398 | 899 | R3TR | DOMA | /BFH/NUMC8
S4HK900398 | 900 | R3TR | DTEL | /BFH/NUMC8
S4HK900398 | 901 | R3TR | TABL | /BFH/MAP_EXPR
S4HK900398 | 902 | R3TR | TTYP | /BFH/TT_EXPRESSIONS
S4HK900398 | 903 | R3TR | TOBJ | /BFH/EXPRESSIONSS
S4HK900398 | 904 | R3TR | FUGR | /BFH/DATA_M
S4HK900398 | 905 | R3TR | DEVC | /BFH/HUB_CORE
S4HK900398 | 906 | R3TR | CLAS | /BFH/CL_ABAP_DATFM
S4HK900398 | 907 | R3TR | CLAS | /BFH/CL_ABAP_DECFM
S4HK900398 | 908 | R3TR | CLAS | /BFH/CL_BALANCE_CHECK
S4HK900398 | 909 | R3TR | CLAS | /BFH/CL_ERRORHDL_DAO
S4HK900398 | 910 | R3TR | CLAS | /BFH/CL_ERRORHDL_EMAIL
S4HK900398 | 911 | R3TR | CLAS | /BFH/CL_ERRORHDL_SRV
S4HK900398 | 912 | R3TR | CLAS | /BFH/CL_ERRORHDL_SRV_AMDP
S4HK900398 | 913 | R3TR | CLAS | /BFH/CL_LOAD
S4HK900398 | 914 | R3TR | CLAS | /BFH/CL_MONITOR_COCKPIT_SRV
S4HK900398 | 915 | R3TR | CLAS | /BFH/CL_MONI_COCKPIT_SRV_AMDP
S4HK900398 | 916 | R3TR | CLAS | /BFH/CL_REVERSAL_SRV
S4HK900398 | 917 | R3TR | DEVC | /BFH/FRAMEWORK
S4HK900398 | 918 | R3TR | PROG | /BFH/UI_ERRORHDL
S4HK900398 | 919 | R3TR | PROG | /BFH/UI_ERRORHDL_EVT_RECVER
S4HK900398 | 920 | R3TR | PROG | /BFH/UI_ERRORHDL_EVT_RECEIVER
S4HK900398 | 921 | R3TR | PROG | /BFH/UI_ERRORHDL_ICON
S4HK900398 | 922 | R3TR | FUGR | /BFH/ACC_DOCUMENT_POST
S4HK900398 | 923 | R3TR | FUGR | /BFH/ACC_PARALLEL_POST
S4HK900398 | 924 | R3TR | FUGR | /BFH/UPD_COMMIT
S4HK900398 | 925 | R3TR | INTF | /BFH/IF_STEP_GEN
S4HK900398 | 926 | R3TR | PROG | /BFH/ACC_PARALLEL_POST01
S4HK900398 | 927 | R3TR | PROG | /BFH/ERRORHDL_UI
S4HK900398 | 928 | R3TR | PROG | /BFH/ERRORHDL_UI_ENH
S4HK900398 | 929 | R3TR | PROG | /BFH/ERRORHDL_UI_ENH_EVT_REV
S4HK900398 | 930 | R3TR | PROG | /BFH/ERRORHDL_UI_ENH_F01
S4HK900398 | 931 | R3TR | PROG | /BFH/ERRORHDL_UI_ENH_SEL
S4HK900398 | 932 | R3TR | PROG | /BFH/ERRORHDL_UI_ENH_TOP
S4HK900398 | 933 | R3TR | PROG | /BFH/ERRORHDL_UI_EVT_RECEIVER
S4HK900398 | 934 | R3TR | PROG | /BFH/ERRORHDL_UI_F01
S4HK900398 | 935 | R3TR | PROG | /BFH/ERRORHDL_UI_SEL
S4HK900398 | 936 | R3TR | PROG | /BFH/ERRORHDL_UI_TOP
S4HK900398 | 937 | R3TR | PROG | /BFH/MASTER_DATA_CHECK
S4HK900398 | 938 | R3TR | PROG | /BFH/MONITOR_COCKPIT_UI_EVT
S4HK900398 | 939 | R3TR | PROG | /BFH/MONITOR_COCKPIT_UI_F01
S4HK900398 | 940 | R3TR | PROG | /BFH/MONITOR_COCKPIT_UI_SEL
S4HK900398 | 941 | R3TR | PROG | /BFH/MONITOR_COCKPIT_UI_TOP
S4HK900398 | 942 | R3TR | PROG | /BFH/REVERSAL_UI
S4HK900398 | 943 | R3TR | SOTR | /BFH/FRAMEWORK
S4HK900398 | 944 | R3TR | SOTS | /BFH/FRAMEWORK
S4HK900398 | 945 | R3TR | CLAS | /BFH/CL_NP_SALV_MODEL
S4HK900398 | 946 | R3TR | CLAS | /BFH/RECORD_COUNT_VALIDATION
S4HK900398 | 947 | R3TR | TRAN | /BFH/ERRORHDL
S4HK900398 | 948 | R3TR | TRAN | /BFH/MONITOR_COCKPIT
S4HK900398 | 949 | R3TR | TRAN | /BFH/REVERSAL
S4HK900398 | 950 | R3TR | TRAN | /BFH/RUN_INTERFACE
S4HK900398 | 951 | R3TR | CLAS | /BFH/CL_XML_CONNECTOR_DEP
S4HK900398 | 952 | R3TR | CLAS | /BFH/CL_CALC_STEP
S4HK900398 | 953 | R3TR | CLAS | /BFH/CL_POSTINGDATE_STEP
S4HK900398 | 954 | R3TR | MSAG | /BFH/CL_MESSAGE
S4HK900398 | 955 | R3TR | CLAS | /BFH/CL_ACC_DOCS_POST
S4HK900398 | 956 | R3TR | CLAS | /BFH/CL_CONNECTOR
S4HK900398 | 957 | R3TR | CLAS | /BFH/CL_CONNECTOR_FACTORY
S4HK900398 | 958 | R3TR | CLAS | /BFH/CL_CONTRA_STEP
S4HK900398 | 959 | R3TR | CLAS | /BFH/CL_CSV_CONNECTOR
S4HK900398 | 960 | R3TR | CLAS | /BFH/CL_EXTRACT
S4HK900398 | 961 | R3TR | CLAS | /BFH/CL_FEEDBACK
S4HK900398 | 962 | R3TR | CLAS | /BFH/CL_FILE_CHUNK_CALC
S4HK900398 | 963 | R3TR | CLAS | /BFH/CL_FIN_BAL_VALIDATION
S4HK900398 | 964 | R3TR | MSAG | /BFH/CONNECTOR
S4HK900398 | 965 | R3TR | CLAS | /BFH/CL_FLATFILE_CONNECTOR
S4HK900398 | 966 | R3TR | CLAS | /BFH/CL_FSG_VALIDATION
S4HK900398 | 967 | R3TR | CLAS | /BFH/CL_GENERATOR_FACTORY
S4HK900398 | 968 | R3TR | CLAS | /BFH/CL_INTERFACE
S4HK900398 | 969 | R3TR | CLAS | /BFH/CL_LOGGER
S4HK900398 | 970 | R3TR | CLAS | /BFH/CL_MASTER_DATA_VALIDATION
S4HK900398 | 971 | R3TR | CLAS | /BFH/CL_PROCESS
S4HK900398 | 972 | R3TR | CLAS | /BFH/CL_PROCESS_FACTORY
S4HK900398 | 973 | R3TR | CLAS | /BFH/CL_RUN_LOG
S4HK900398 | 974 | R3TR | CLAS | /BFH/CL_S1_LOAD
S4HK900398 | 975 | R3TR | CLAS | /BFH/CL_STAGING_STEP
S4HK900398 | 976 | R3TR | CLAS | /BFH/CL_TRANSFORM_GENERATOR
S4HK900398 | 977 | R3TR | CLAS | /BFH/CL_UTIL
S4HK900398 | 978 | R3TR | CLAS | /BFH/CX_CONNECTOR
S4HK900398 | 979 | R3TR | CLAS | /BFH/CL_DAO_ERRORHDL
S4HK900398 | 980 | R3TR | CLAS | /BFH/CL_HDT_VALIDATION
S4HK900398 | 981 | R3TR | CLAS | /BFH/CL_MAP_STEP
S4HK900398 | 982 | R3TR | CLAS | /BFH/CL_NORMALFSG
S4HK900398 | 983 | R3TR | CLAS | /BFH/CL_POSTING_PREP_TST
S4HK900398 | 984 | R3TR | CLAS | /BFH/CL_S2_AGGREGATOR
S4HK900398 | 985 | R3TR | CLAS | /BFH/CL_S2_LOAD
S4HK900398 | 986 | R3TR | CLAS | /BFH/CL_STAGING_STEP_AGG
S4HK900398 | 987 | R3TR | MSAG | /BFH/CL_TEST_MESSAGE
S4HK900398 | 988 | R3TR | MSAG | /BFH/M_CONNECTOR
S4HK900398 | 989 | R3TR | PROG | /BFH/ERRORHDL_UI_D
S4HK900398 | 990 | R3TR | CLAS | /BFH/ERRORHDL_EMAIL
S4HK900398 | 991 | R3TR | PROG | /BFH/ERRORHDL_UI_ICON
S4HK900398 | 992 | R3TR | CLAS | /BFH/CL_ERRORHDL_EMAIL_TEST
S4HK900398 | 993 | R3TR | ENHO | /BFH/S2_AGGREGATION
S4HK900398 | 994 | R3TR | PROG | /BFH/GENERATE_INTERFACE
S4HK900398 | 995 | R3TR | PROG | /BFH/RUN_INTERFACE
S4HK900398 | 996 | R3TR | MSAG | /BFH/VALIDATION
S4HK900398 | 997 | R3TR | CLAS | /BFH/CL_INIT_STEP
S4HK900398 | 998 | R3TR | CLAS | /BFH/CL_TRANSFORM
S4HK900398 | 999 | R3TR | CLAS | /BFH/CL_CLEANUP
S4HK900398 | 1000 | R3TR | CLAS | /BFH/CL_FEEDBACK_REPORT
S4HK900398 | 1001 | R3TR | INTF | /BFH/IF_STEP_TYPE
S4HK900398 | 1002 | R3TR | PROG | /BFH/DISPLAY_FSG_DATA
S4HK900398 | 1003 | R3TR | PROG | /BFH/RUNTIMEANALYSIS_UI_STAO01
S4HK900398 | 1004 | R3TR | PROG | /BFH/RUNTIMEANALYSIS_UI_STAO02
S4HK900398 | 1005 | R3TR | PROG | /BFH/RUNTIMEANALYSIS_UI_TOP
S4HK900398 | 1006 | R3TR | PROG | /BFH/RUN_FEEDBACK
S4HK900398 | 1007 | R3TR | CLAS | /BFH/CL_FILTER_STEP
S4HK900398 | 1008 | R3TR | CLAS | /BFH/CL_CONFIG_UPLOAD
S4HK900398 | 1009 | R3TR | CLAS | /BFH/CL_TRANSPORT_OBJECTS
S4HK900398 | 1010 | R3TR | CLAS | /BFH/CX_TRANSPORT_OBJECTS
S4HK900398 | 1011 | R3TR | MSAG | /BFH/CONFIG_UPLOAD
S4HK900398 | 1012 | R3TR | PROG | /BFH/SOURCE_TABLE_UPLOAD
S4HK900398 | 1013 | R3TR | PROG | /BFH/CONFIG_UPLOAD
S4HK900398 | 1014 | R3TR | CLAS | /BFH/CL_CUSTOM_STEP
S4HK900398 | 1015 | R3TR | MSAG | /BFH/M_SRC_TABL_GENE
S4HK900398 | 1016 | R3TR | CLAS | /BFH/CL_AGGREGATE_STEP
S4HK900398 | 1017 | R3TR | CLAS | /BFH/CL_BETRAGS_STEP
S4HK900398 | 1018 | R3TR | CLAS | /BFH/CL_NORMALISE_STEP
S4HK900398 | 1019 | R3TR | CLAS | /BFH/CL_VALIDATE_STEP
S4HK900398 | 1020 | R3TR | CLAS | /BFH/CL_MAP_STEP_DEP
S4HK900398 | 1021 | R3TR | CLAS | /BFH/CL_TEMP_FILTER_STEP
S4HK900398 | 1022 | R3TR | PROG | /BFH/TEST
S4HK900398 | 1023 | R3TR | PROG | /BFH/DEMO_AMDP_VS_OPEN_SQL
S4HK900398 | 1024 | R3TR | CLAS | /BFH/CL_TABLE_GENERATOR
S4HK900398 | 1025 | R3TR | CLAS | /BFH/CX_TABLE_GENERATOR
S4HK900398 | 1026 | R3TR | INTF | /BFH/IF_GENERATOR
S4HK900398 | 1027 | R3TR | PROG | /BFH/GENERATE_TABLES
S4HK900398 | 1028 | R3TR | PROG | /BFH/FILL_DATA_SEGMNT
S4HK900398 | 1029 | R3TR | CLAS | /BFH/CL_ZERO_AMOUNT_FLTR_STEP
S4HK900398 | 1030 | R3TR | PROG | /BFH/INTERFACE_COCKPIT_UI
S4HK900398 | 1031 | R3TR | CLAS | /BFH/CL_RUNTIMEANLYS_SRV
S4HK900398 | 1032 | R3TR | PROG | /BFH/INTERFACE_COCKPIT
S4HK900398 | 1033 | R3TR | PROG | /BFH/INTERFACE_COCKPIT_PAI
S4HK900398 | 1034 | R3TR | PROG | /BFH/INTERFACE_COCKPIT_PBO
S4HK900398 | 1035 | R3TR | CLAS | /BFH/CL_DPD_DOCK_CONTAINER_FAC
S4HK900398 | 1036 | R3TR | CLAS | /BFH/CL_DOCK_CONTAINER_FACTORY
S4HK900398 | 1037 | R3TR | MSAG | /BFH/M_MAND_MAP_MISS
S4HK900398 | 1038 | R3TR | MSAG | /BFH/M_EXTRACT_VALID
S4HK900398 | 1039 | R3TR | CLAS | /BFH/CL_DPD_MOD_DBT
S4HK900398 | 1040 | R3TR | CLAS | /BFH/CL_DPD_ITAB_DEC
S4HK900398 | 1041 | R3TR | CLAS | /BFH/CL_ST_TEXT_EDITOR
S4HK900398 | 1042 | R3TR | ENHO | /BFH/GENERATION
S4HK900398 | 1043 | R3TR | CLAS | /BFH/CL_STEP_FACTORY_DEP
S4HK900398 | 1044 | R3TR | CLAS | /BFH/CL_STEP_FACTORY
S4HK900398 | 1045 | R3TR | CLAS | /BFH/CX_GENERATOR
S4HK900398 | 1046 | R3TR | CLAS | /BFH/CX_GENERATOR_NEW
S4HK900398 | 1047 | R3TR | CLAS | /BFH/CX_CONFIG_UPLOAD
S4HK900398 | 1048 | R3TR | MSAG | /BFH/M_TBD
S4HK900398 | 1049 | R3TR | CLAS | /BFH/CL_MAP_STEP_WITH_ANALYSE
S4HK900398 | 1050 | R3TR | CLAS | /BFH/CL_MAP_STEP_NEW
S4HK900398 | 1051 | R3TR | CLAS | /BFH/CL_DPD_ITAB_DEC_INTERFACE
S4HK900398 | 1052 | R3TR | CLAS | /BFH/CX_FRAMEWORK
S4HK900398 | 1053 | R3TR | CLAS | /BFH/CX_FRAMEWORK_TEST
S4HK900398 | 1054 | R3TR | MSAG | /BFH/M_TRANSP_OBJ
S4HK900398 | 1055 | R3TR | MSAG | /BFH/SRC_TABL_GEN
S4HK900398 | 1056 | R3TR | MSAG | /BFH/GENERATOR
S4HK900398 | 1057 | R3TR | CLAS | /BFH/CL_XML_CONNECTOR
S4HK900398 | 1058 | R3TR | CLAS | /BFH/CL_XML_CONNECTOR_GENERIC
S4HK900398 | 1059 | R3TR | CLAS | /BFH/CL_LOGGER_DEP
S4HK900398 | 1060 | R3TR | MSAG | /BFH/LOAD
S4HK900398 | 1061 | R3TR | PROG | /BFH/R_INTERFACE_COCKPIT_TOP
S4HK900398 | 1062 | R3TR | PROG | /BFH/R_INTERFACE_COCKPIT_01
S4HK900398 | 1063 | R3TR | PROG | /BFH/R_INTERFACE_COCKPIT_02
S4HK900398 | 1064 | R3TR | PROG | /BFH/R_INTERFACE_COCKPIT_F01
S4HK900398 | 1065 | R3TR | MSAG | /BFH/MAND_MAP_MISS
S4HK900398 | 1066 | R3TR | FUGR | /BFH/UI_RUNTIME_ANALYS
S4HK900398 | 1067 | R3TR | CLAS | /BFH/CL_UI_SUB_FUNCTIONS
S4HK900398 | 1068 | R3TR | CLAS | /BFH/CL_UI_SUB_SCREENS
S4HK900398 | 1069 | R3TR | FUGR | /BFH/UI_SUB_FUNCTIONS
S4HK900398 | 1070 | R3TR | FUGR | /BFH/UI_SUB_SCREENS
S4HK900398 | 1071 | R3TR | MSAG | /BFH/M_FRAMEWORK
S4HK900398 | 1072 | R3TR | CLAS | /BFH/CL_UI_RUNTIME_ANLYS
S4HK900398 | 1073 | R3TR | MSAG | /BFH/FRAMEWORK
S4HK900398 | 1074 | R3TR | PROG | /BFH/R_INTERFACE_COCKPIT
S4HK900398 | 1075 | R3TR | PROG | /BFH/REP_INTERFACE_COCKPIT
S4HK900398 | 1076 | R3TR | PROG | /BFH/REP_INTERFACE_COCKPIT_TOP
S4HK900398 | 1077 | R3TR | PROG | /BFH/REP_INTERFACE_COCKPIT_01
S4HK900398 | 1078 | R3TR | PROG | /BFH/REP_INTERFACE_COCKPIT_02
S4HK900398 | 1079 | R3TR | PROG | /BFH/REP_INTERFACE_COCKPIT_F01
S4HK900398 | 1080 | R3TR | PROG | /BFH/RUNTIMEANALYSIS_UI
S4HK900398 | 1081 | R3TR | TABL | /BFH/INTERFACE_TREE
S4HK900398 | 1082 | R3TR | DTEL | /BFH/NODE1
S4HK900398 | 1083 | R3TR | DOMA | /BFH/NODE1
S4HK900398 | 1084 | R3TR | CLAS | /BFH/CL_FIXEDLENGTH_CONN_DEP
S4HK900398 | 1085 | R3TR | CLAS | /BFH/CL_FIXEDLENGTH_CONNECTOR
S4HK900398 | 1086 | R3TR | CLAS | /BFH/CL_FIXEDLEN_CONNECTOR_GEN
S4HK900398 | 1087 | R3TR | PROG | /BFH/UI_LOOKUP_VALUES_RPT
S4HK900398 | 1088 | R3TR | PROG | /BFH/VALUE_MAPPING_COCKPIT_UI
S4HK900398 | 1089 | R3TR | PROG | /BFH/VALUE_MAPPING_UIC01
S4HK900398 | 1090 | R3TR | PROG | /BFH/VALUE_MAPPING_UIO01
S4HK900398 | 1091 | R3TR | PROG | /BFH/VALUE_MAPPING_UII01
S4HK900398 | 1092 | R3TR | PROG | /BFH/UI_LOOKUP_COCKPIT
S4HK900398 | 1093 | R3TR | PROG | /BFH/UI_LOOKUP_COCKPITC01
S4HK900398 | 1094 | R3TR | PROG | /BFH/UI_LOOKUP_COCKPITI01
S4HK900398 | 1095 | R3TR | PROG | /BFH/UI_LOOKUP_COCKPITO01
S4HK900398 | 1096 | R3TR | TABL | /BFH/BAPIRET2
S4HK900398 | 1097 | R3TR | CLAS | /BFH/CL_DERIVE_ACCOUNT_NO_STEP
S4HK900398 | 1098 | R3TR | TRAN | /BFH/ICC
S4HK900398 | 1099 | R3TR | TRAN | /BFH/INTERFACE_CONF
S4HK900398 | 1100 | R3TR | PROG | /BFH/REP_MSG_COCKPIT
S4HK900398 | 1101 | R3TR | PROG | /BFH/REP_MSG_COCKPIT_TOP
S4HK900398 | 1102 | R3TR | PROG | /BFH/REP_MSG_COCKPIT_01
S4HK900398 | 1103 | R3TR | PROG | /BFH/REP_MSG_COCKPIT_02
S4HK900398 | 1104 | R3TR | PROG | /BFH/REP_MSG_COCKPIT_F01
S4HK900398 | 1105 | R3TR | TRAN | /BFH/VALUE_MAP_UI
S4HK900398 | 1106 | R3TR | CLAS | /BFH/CL_RUNTIMEANALYSIS_DELETE
S4HK900398 | 1107 | R3TR | CLAS | /BFH/CL_RUNTIMEANALYSIS_ALV
S4HK900398 | 1108 | R3TR | TRAN | /BFH/CONFIG_UPLOAD
S4HK900398 | 1109 | R3TR | TRAN | /BFH/CONFIG_UPLOAD_B
S4HK900398 | 1110 | R3TR | TRAN | /BFH/GENERATE_TABLES
S4HK900398 | 1111 | R3TR | CLAS | /BFH/CL_AUFNR_KOSTL_VAL
S4HK900398 | 1112 | R3TR | PROG | /BFH/RUNTIMEANALYSIS
S4HK900398 | 1113 | R3TR | PROG | /BFH/ACCOUNT_DOCUMENT_POST
S4HK900398 | 1114 | R3TR | CLAS | /BFH/CL_PACKAGE_GENERATOR
S4HK900398 | 1115 | R3TR | PROG | /BFH/GENERATE_PACKAGES
S4HK900398 | 1116 | R3TR | CLAS | /BFH/CL_STEP_GENERATOR
S4HK900398 | 1117 | R3TR | DEVC | /BFH/TEST_DATA
S4HK900398 | 1118 | R3TR | TABL | /BFH/S1_BKPFCON
S4HK900398 | 1119 | R3TR | TABL | /BFH/S1_BSEGCON
S4HK900398 | 1120 | R3TR | CLAS | /BFH/CL_DATA_RECON
S4HK900398 | 1121 | R3TR | DDLS | /BFH/TST_CDS
S4HK900398 | 1122 | R3TR | PROG | /BFH/DATA_COPY_TEST
S4HK900398 | 1123 | R3TR | PROG | /BFH/DATA_MODIFY_TEST
S4HK900398 | 1124 | R3TR | PROG | /BFH/TST_CLEANUP
S4HK900398 | 1125 | R3TR | TABL | /BFH/TMP_SRC2UTL
S4HK900398 | 1126 | R3TR | TABL | /BFH/TMP_UTL2LVA
S4HK900398 | 1127 | R3TR | DDLS | /BFH/TMP_LKP_VAL
S4HK900398 | 1128 | R3TR | TABL | /BFH/TMP_AGNINF
S4HK900398 | 1129 | R3TR | TABL | /BFH/TMP_DATAFIE
S4HK900418 | 1 | R3TR | TABU | /BFH/LKP_DRIVERS
S4HK900418 | 2 | R3TR | TABU | /BFH/LKP_VALUES

## Discussion Points
Item | Type | Description | Comments
1 | D | What is the best date to have the migration in order to minimize cherry picking and impact on current work (i.e.: interfaces roll-in) | Is going to be tomorrow. Therefore need to have the transports ready. Sandbox should be available until the end of March.
2 | D | Who is going to be responsible to transport and check non-/BFH/ objects at target system? | Jose
3 | D | For GB a HANA DB View was created but needs to be revisited as this has licensing impact.
4 | D | What is the impact of having different client Numbers in DS4 (Clients 180 (ABAP / Customizing / Master Data -> SCC1) and 181 (Unit Test)) when compared to S4H? | There should be no impact but this needs to be confirmed.
5 | A | Define what are the folder requirements (1 per BU + Archive) | Previously they had 3 folders: Inbound, Working, Archive
6 | D | Which customing tables entries should be moved to DS4? | Lookup Drivers, Lookup Values